## Instructions
AEGIS FDE Day-wise Task Tracker (management)
Source of truth: AEGIS_FDE_DAYWISE_TASK_DISTRIBUTION.md (v1.4) + this workbook.
Regenerate: python -B submission/artefacts/ProjectPlan/export_daywise_tracker.py
Columns (tracking)
Date/Day · Module/Workstream · Task · Task Details · Assigned To · Priority · Status ·
Start / Expected / Actual Completion · Dependencies · Blockers/Remarks · Completion %
Preserved audit columns: Task ID, Reviewer, Gate, FINAL ref, Evaluation criteria, Result, Evidence path
Dropdowns
Priority: Low ¦ Medium ¦ High ¦ Critical
Status: Not Started ¦ In Progress ¦ Blocked ¦ Completed ¦ On Hold
Result: PASS ¦ FAIL ¦ CONDITIONAL ¦ N/A
Formatting
- Header frozen; filters on; Task + Task Details wrap text
- Red tint = Blocked; amber tint = Overdue (Expected Completion < today and not Completed)
- Completion Percentage uses % format (enter 0.5 for 50%)
Rules: author ≠ sole approver · Agents OFF until G4 · work under submission/ only
Validated Task Details for all 91 tasks before Excel generation.
Calendar: D1 = 2026-08-04 (Option B+ sequential session days).

## Task_Tracker
Date / Day | Module / Workstream | Task ID | Task | Task Details | Assigned To | Priority | Status | Start Date | Expected Completion Date | Actual Completion Date | Dependencies | Blockers / Remarks | Completion Percentage | Reviewer | Gate | FINAL ref | Evaluation criteria | Result | Evidence path
D1 | P0 Preflight | D1-T1 | Hour-0 preflight; archive VALIDATION_REPORT.json | What to implement: Hour-0 preflight; archive VALIDATION_REPORT.json Expected functionality: Run `python -B run_capstone.py --check` once. Copy/archive VALIDATION_REPORT.json under submission/evidence/ with timestamp. Do not re-run until defence unless challenge tree integrity is in doubt. Log command + result in decision log. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §4.2, §8 P0. Reviewer FDE-5 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Command uses python -B; report status PASS; archive path under submission/evidence/; timestamp logged | FDE-3 | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | Kickoff / package available |  | 0% | FDE-5 | Preflight | §4.2, §8 P0 | Command uses python -B; report status PASS; archive path under submission/evidence/; timestamp logged
D1 | P0 Preflight | D1-T2 | Scaffold submission dirs; -B convention | What to implement: Scaffold submission dirs; -B convention Expected functionality: Create submission tree via check_submission_structure.py --scaffold. Ensure app/, src/, tests/, evaluation/, artefacts/, evidence/, runbooks/, scripts/ exist. Document that all Python invocations use python -B. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §7.2, §8 P0. Reviewer FDE-1 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: check_submission_structure.py --scaffold PASS; dirs app/src/tests/evaluation/artefacts/evidence/runbooks/scripts exist | FDE-3 | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | Kickoff / package available |  | 0% | FDE-1 | Preflight | §7.2, §8 P0 | check_submission_structure.py --scaffold PASS; dirs app/src/tests/evaluation/artefacts/evidence/runbooks/scripts exist
D1 | P0 Preflight | D1-T3 | Team charter + SCQA; open Assumptions/Decision/RAID logs | What to implement: Team charter + SCQA; open Assumptions/Decision/RAID logs Expected functionality: Write short charter (SCQA + seats + prohibited AI actions). Create assumptions, decision, and RAID logs under submission/evidence/. Name FDE-1…5 ↔ P1…P5. Confirm dual-track honesty language. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P0, §17, §21. Reviewer FDE-4 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Charter lists prohibited AI actions; logs exist under submission/evidence/; seats named | FDE-1 | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | Kickoff / package available |  | 0% | FDE-4 | Preflight | §8 P0, §17, §21 | Charter lists prohibited AI actions; logs exist under submission/evidence/; seats named
D1 | P0 Preflight | D1-T4 | Case + inject catalogue skim; D01–D13 hotspots | What to implement: Case + inject catalogue skim; D01–D13 hotspots Expected functionality: Read INTEGRATED_CASE and injects.json. Produce hotspot list for D01–D13 (batch/PV/supply/privacy/security). Explicitly do not “fix” deliberate conflicts or normalize units/IDs. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §3, §8 P0. Reviewer FDE-3 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Written hotspot list citing INTEGRATED_CASE / injects.json; no conflict “fixes” | FDE-2 | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | Kickoff / package available |  | 0% | FDE-3 | Preflight | §3, §8 P0 | Written hotspot list citing INTEGRATED_CASE / injects.json; no conflict “fixes”
D1 | P0 Preflight | D1-T5 | Prohibited-action catalogue from ai_use_boundaries + decision_rights | What to implement: Prohibited-action catalogue from ai_use_boundaries + decision_rights Expected functionality: Extract forbid lists from challenge CSVs. Map each forbid to Workflow A/B/C. Catalogue becomes input to G1 artefacts and G3/G4 contracts. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §1, §3.2, §8 P1 prep. Reviewer FDE-5 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Catalogue covers batch/PV/supply forbids; cites CSV paths; maps to WF A/B/C | FDE-4 | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | Kickoff / package available |  | 0% | FDE-5 | Preflight | §1, §3.2, §8 P1 prep | Catalogue covers batch/PV/supply forbids; cites CSV paths; maps to WF A/B/C
D1 | P0 Preflight | D1-T6 | Security/privacy stop lines; flag INJ-065/066/067 | What to implement: Security/privacy stop lines; flag INJ-065/066/067 Expected functionality: Write deny-by-default stop lines for tool poisoning, unsigned tools, stale auth. Reference INJ-065/066/067. Feed into threat artefact and failing tests later. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §3.4, §11. Reviewer FDE-4 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Stop lines written; three inject IDs referenced; deny-by-default stated | FDE-5 | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | Kickoff / package available |  | 0% | FDE-4 | Preflight | §3.4, §11 | Stop lines written; three inject IDs referenced; deny-by-default stated
D1 | P0 Preflight | D1-T7 | Ratify AEGIS_PROJECT_PLAN_FINAL.md | What to implement: Ratify AEGIS_PROJECT_PLAN_FINAL.md Expected functionality: Team agrees FINAL v1.1+ is governing SoT. Decision-log entry with version, date, dual-track honesty. Supersedes V1–V4 for execution. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §21. Reviewer FDE-1 records (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Decision-log entry: ratified version + date; dual-track honesty acknowledged | All | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | D1-T1; D1-T2; D1-T3 |  | 0% | FDE-1 records | Preflight | §21 | Decision-log entry: ratified version + date; dual-track honesty acknowledged
D1 | P0 Preflight | D1-T8 | Eval step 1: document brownfield understanding | What to implement: Eval step 1: document brownfield understanding Expected functionality: Capture workflows, I/O, evidence sources, tools/APIs, rules/restrictions, existing tests, failure handling, human approval points. Cite starter/ and contracts. Write to submission/evaluation/README.md or evidence/repo_understanding.md. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.8 step 1. Reviewer FDE-2 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Written note covering all eight topics; cites starter/ + contracts | FDE-5 (+FDE-3) | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | D1-T4 |  | 0% | FDE-2 | Preflight | §11.8 step 1 | Written note covering all eight topics; cites starter/ + contracts
D1 | P0 Preflight | D1-T9 | Create finops_delivery_log.csv; seed D1 rows | What to implement: Create finops_delivery_log.csv; seed D1 rows Expected functionality: Create submission/evidence/finops_delivery_log.csv with columns: date, task_id, chat_sessions, files_attached, agent_iterations, terminal_commands, files_modified, failed_attempts, full_suite_runs, task_outcome. Each seat logs ≥1 D1 row; agent_iterations=0 until G4. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.9. Reviewer FDE-5 (author ≠ sole approver). Gate context: Preflight. Expected output / completion criteria: Header matches §0.3; each seat has ≥1 row for D1; agent_iterations=0 | FDE-1 | Critical | Not Started | 2026-08-04 | 2026-08-04 |  | D1-T3 |  | 0% | FDE-5 | Preflight | §11.9 | Header matches §0.3; each seat has ≥1 row for D1; agent_iterations=0
D2 | P1 Discovery / G1 | D2-T1 | Draft artefacts 01–04 | What to implement: Draft artefacts 01–04 Expected functionality: Produce problem/value (01), business case (02), stakeholders (03), AI blueprint/boundaries (04). Cite BR-01, kpi_conflicts, stakeholders, ai_use_boundaries. Label FACT vs ASSUMPTION. Meet substantive length rules. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P1, §12. Reviewer FDE-4 (01–03), FDE-5 (04) (author ≠ sole approver). Gate context: G1. Expected output / completion criteria: Each cites BR-01 / kpi_conflicts / stakeholders / ai_use_boundaries as applicable; FACT/ASSUMPTION labels; ≥ substantive length | FDE-1 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T7 |  | 0% | FDE-4 (01–03), FDE-5 (04) | G1 | §8 P1, §12 | Each cites BR-01 / kpi_conflicts / stakeholders / ai_use_boundaries as applicable; FACT/ASSUMPTION labels; ≥ substantive length
D2 | P1 Discovery / G1 | D2-T2 | No-AI comparison + stop/pivot | What to implement: No-AI comparison + stop/pivot Expected functionality: Compare master_data_repair vs rules vs GenAI paths. Document stop/pivot/pause/abstain triggers including prohibited autonomy. Keep honest about when AI is not needed. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §3.3, §3.4. Reviewer FDE-5 (author ≠ sole approver). Gate context: G1. Expected output / completion criteria: master_data_repair / rules / genai table present; stop triggers include prohibited autonomy | FDE-1 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D2-T1 |  | 0% | FDE-5 | G1 | §3.3, §3.4 | master_data_repair / rules / genai table present; stop triggers include prohibited autonomy
D2 | P1 Discovery / G1 | D2-T3 | Lock production NFRs @ G1 | What to implement: Lock production NFRs @ G1 Expected functionality: Fill all 8 NFR rows (availability through compliance). No certification or ISO-conformant overclaim. Lock table at G1 for later soak/FinOps checks. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §5.3. Reviewer FDE-5 (author ≠ sole approver). Gate context: G1. Expected output / completion criteria: All 8 NFR rows filled; no certification overclaim | FDE-1 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D2-T1 |  | 0% | FDE-5 | G1 | §5.3 | All 8 NFR rows filled; no certification overclaim
D2 | P1 Discovery / G1 | D2-T4 | Stakeholder facts → artefact 03 | What to implement: Stakeholder facts → artefact 03 Expected functionality: Feed 15 roles and 5 conflicts into artefact 03. Preserve AI authority as none/draft-only. Surface Quality vs Manufacturing tension without resolving it away. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §6.3. Reviewer FDE-4 (author ≠ sole approver). Gate context: G1. Expected output / completion criteria: 15 roles / 5 conflicts referenced; AI authority none/draft only preserved | FDE-2 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T4 |  | 0% | FDE-4 | G1 | §6.3 | 15 roles / 5 conflicts referenced; AI authority none/draft only preserved
D2 | P1 Discovery / G1 | D2-T5 | Script stubs setup/run/test/evaluate/reset | What to implement: Script stubs setup/run/test/evaluate/reset Expected functionality: Create five named scripts under submission/scripts/ (stubs OK). Document invocation in README or runbook stub. Wire later in P5–P7. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §7.2. Reviewer FDE-5 (author ≠ sole approver). Gate context: G1. Expected output / completion criteria: Five named scripts exist (stubs OK); documented invocation | FDE-3 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T2 |  | 0% | FDE-5 | G1 | §7.2 | Five named scripts exist (stubs OK); documented invocation
D2 | P1 Discovery / G1 | D2-T6 | Review 03; Quality vs Mfg conflict note | What to implement: Review 03; Quality vs Mfg conflict note Expected functionality: Independent review of artefact 03. Own the Quality vs Manufacturing conflict in writing. Author ≠ sole approver. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §6.3, §12. Reviewer FDE-1 (ack) (author ≠ sole approver). Gate context: G1. Expected output / completion criteria: Written review finding; conflict owned; no SoD breach | FDE-4 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D2-T1; D2-T4 |  | 0% | FDE-1 (ack) | G1 | §6.3, §12 | Written review finding; conflict owned; no SoD breach
D2 | P1 Discovery / G1 | D2-T7 | Review 04; NFR sec/privacy rows | What to implement: Review 04; NFR sec/privacy rows Expected functionality: Review artefact 04 and NFR security/privacy bars. Confirm prohibited uses are explicit and measurable. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §12, §5.3. Reviewer FDE-1 (ack) (author ≠ sole approver). Gate context: G1. Expected output / completion criteria: Review confirms prohibited uses + privacy/security NFR bars | FDE-5 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D2-T1; D2-T3 |  | 0% | FDE-1 (ack) | G1 | §12, §5.3 | Review confirms prohibited uses + privacy/security NFR bars
D3 | P2 Domain | D3-T1 | Draft 05 DDD + 06 Data gov | What to implement: Draft 05 DDD + 06 Data gov Expected functionality: Bounded contexts for WF A/B/C. State ALCOA+ and no silent normalize. Artefact 06 must be hard-gate aware (authority, effective date, units). Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P2, §12. Reviewer FDE-3 (05), FDE-4 (06) (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Bounded contexts for A/B/C; ALCOA+/no silent normalize stated; 06 hard-gate aware | FDE-2 | High | Not Started | 2026-08-06 | 2026-08-06 |  | G1 (D2) |  | 0% | FDE-3 (05), FDE-4 (06) |  | §8 P2, §12 | Bounded contexts for A/B/C; ALCOA+/no silent normalize stated; 06 hard-gate aware
D3 | P2 Domain | D3-T2 | Start 84-inject register mirror | What to implement: Start 84-inject register mirror Expected functionality: Mirror INJECT_TEST_COVERAGE under submission/evaluation/. Leave challenge CSV untouched. All rows start NOT_RUN; progress must be countable. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Mirror path under submission/evaluation/; challenge CSV untouched; progress countable | FDE-2 | High | Not Started | 2026-08-06 | 2026-08-06 |  | D1-T4 |  | 0% | FDE-4 |  | §11.1 | Mirror path under submission/evaluation/; challenge CSV untouched; progress countable
D3 | P2 Domain | D3-T3 | RTM skeleton 09; RELATIONSHIP_MODEL checker design | What to implement: RTM skeleton 09; RELATIONSHIP_MODEL checker design Expected functionality: Start artefact 09 RTM. Design checker that cites RELATIONSHIP_MODEL.csv and fails closed on ambiguous identity links. Unique RTM IDs. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P2, §13. Reviewer FDE-5 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Checker design cites RELATIONSHIP_MODEL.csv; RTM IDs unique | FDE-3 | High | Not Started | 2026-08-06 | 2026-08-06 |  | D3-T1 |  | 0% | FDE-5 |  | §8 P2, §13 | Checker design cites RELATIONSHIP_MODEL.csv; RTM IDs unique
D3 | P2 Domain | D3-T4 | Authority/provenance rules for 06; INJ-031 flag | What to implement: Authority/provenance rules for 06; INJ-031 flag Expected functionality: Rules require status, authority, effective date. Log validation ambiguity as conflict (do not invent truth). Flag INJ-031. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P2, §11. Reviewer FDE-2 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Rules require status/authority/effective date; validation ambiguity logged as conflict | FDE-4 | High | Not Started | 2026-08-06 | 2026-08-06 |  | Prior day exit (D2); seat capacity |  | 0% | FDE-2 |  | §8 P2, §11 | Rules require status/authority/effective date; validation ambiguity logged as conflict
D3 | P2 Domain | D3-T5 | Privacy/residency flags in register (D09) | What to implement: Privacy/residency flags in register (D09) Expected functionality: Tag INJ-059–064 in inject register. Do not silently minimize GxP holds for privacy convenience. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.1 D09. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: INJ-059–064 rows tagged; no silent minimization of GxP holds | FDE-5 | High | Not Started | 2026-08-06 | 2026-08-06 |  | Prior day exit (D2); seat capacity |  | 0% | FDE-4 |  | §11.1 D09 | INJ-059–064 rows tagged; no silent minimization of GxP holds
D3 | P2 Domain | D3-T6 | Brownfield/TOM impact notes; global vs local conflict | What to implement: Brownfield/TOM impact notes; global vs local conflict Expected functionality: Capture brownfield and TOM notes for artefact 26 later. Record global vs local conflict without premature resolution. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §6.3. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Notes exist for later artefact 26; conflict not prematurely resolved | FDE-1 | High | Not Started | 2026-08-06 | 2026-08-06 |  | Prior day exit (D2); seat capacity |  | 0% | FDE-4 |  | §6.3 | Notes exist for later artefact 26; conflict not prematurely resolved
D3 | P2 Domain | D3-T7 | Eval step 2: design eval-set coverage matrix | What to implement: Eval step 2: design eval-set coverage matrix Expected functionality: Design cases: normal, edge, adversarial, metamorphic, outage. Include required/prohibited behaviours, escalation, hard-gate status. Store under evaluation/datasets/. expected_answer_included=no. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.8 step 2. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Matrix under datasets/; maps to WF A/B/C + ≥1 row per suite family; expected_answer_included=no | FDE-5 (+FDE-2) | High | Not Started | 2026-08-06 | 2026-08-06 |  | D1-T8; D3-T2 |  | 0% | FDE-4 |  | §11.8 step 2 | Matrix under datasets/; maps to WF A/B/C + ≥1 row per suite family; expected_answer_included=no
D4 | P2 Domain / G2 | D4-T1 | Complete 07 + 08 (KG + simpler alternative) | What to implement: Complete 07 + 08 (KG + simpler alternative) Expected functionality: Finish ontology/KG artefacts. Artefact 08 must include simpler-alternative benchmark. No mandatory KG claim without evidence. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P2, §12, §20. Reviewer FDE-3 (author ≠ sole approver). Gate context: G2. Expected output / completion criteria: 08 includes simpler-alternative benchmark; no mandatory KG claim without evidence | FDE-2 | Critical | Not Started | 2026-08-07 | 2026-08-07 |  | D3-T1 |  | 0% | FDE-3 | G2 | §8 P2, §12, §20 | 08 includes simpler-alternative benchmark; no mandatory KG claim without evidence
D4 | P2 Domain / G2 | D4-T2 | Inject register: all 84 off NOT_RUN or declared gap | What to implement: Inject register: all 84 off NOT_RUN or declared gap Expected functionality: Every inject row either planned/mapped or declared gap in RAID/manifest. Count must equal 84. Never delete or silently resolve challenge rows. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.1. Reviewer FDE-1 (author ≠ sole approver). Gate context: G2. Expected output / completion criteria: Count = 84; gaps in RAID/manifest; challenge CSV unmodified | FDE-2 | Critical | Not Started | 2026-08-07 | 2026-08-07 |  | D3-T2; D3-T7 |  | 0% | FDE-1 | G2 | §11.1 | Count = 84; gaps in RAID/manifest; challenge CSV unmodified
D4 | P2 Domain / G2 | D4-T3 | RTM↔inject links; knowledge_catalog authority+hash stub | What to implement: RTM↔inject links; knowledge_catalog authority+hash stub Expected functionality: Link RTM IDs to injects. Stub catalog gate that rejects superseded/untrusted sources when hash/status fail. Record demo evidence. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §13, §8 P2. Reviewer FDE-5 (author ≠ sole approver). Gate context: G2. Expected output / completion criteria: Stub rejects superseded/untrusted when hash/status fail; demo recorded | FDE-3 | Critical | Not Started | 2026-08-07 | 2026-08-07 |  | D3-T3 |  | 0% | FDE-5 | G2 | §13, §8 P2 | Stub rejects superseded/untrusted when hash/status fail; demo recorded
D4 | P2 Domain / G2 | D4-T4 | Independent conflict review (ID/unit/time/authority/lineage) | What to implement: Independent conflict review (ID/unit/time/authority/lineage) Expected functionality: G2 independent review: list open conflicts. Zero “cleaned” values presented as truth. Supports G2 pass criteria. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8.2 G2. Reviewer FDE-1 (author ≠ sole approver). Gate context: G2. Expected output / completion criteria: Written list of open conflicts; zero cleaned values presented as truth | FDE-4 | Critical | Not Started | 2026-08-07 | 2026-08-07 |  | D4-T2 |  | 0% | FDE-1 | G2 | §8.2 G2 | Written list of open conflicts; zero cleaned values presented as truth
D4 | P2 Domain / G2 | D4-T5 | Spot-check sensitive injects INJ-041/059–064 | What to implement: Spot-check sensitive injects INJ-041/059–064 Expected functionality: Deep-read sensitive privacy/access injects. Log findings and purpose/access limits for later privacy artefact and suites. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: G2. Expected output / completion criteria: Findings logged; access/purpose limits noted | FDE-5 | Critical | Not Started | 2026-08-07 | 2026-08-07 |  | Prior day exit (D3); seat capacity |  | 0% | FDE-4 | G2 | §11.1 | Findings logged; access/purpose limits noted
D4 | P2 Domain / G2 | D4-T6 | Business challenge to unjustified KG | What to implement: Business challenge to unjustified KG Expected functionality: Challenge any KG scope that lacks value evidence. Accept/reject with rationale recorded for innovation slot / artefact 08. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §20, §8.2. Reviewer FDE-2 (author ≠ sole approver). Gate context: G2. Expected output / completion criteria: Review note accept/reject KG scope with rationale | FDE-1 | Critical | Not Started | 2026-08-07 | 2026-08-07 |  | Prior day exit (D3); seat capacity |  | 0% | FDE-2 | G2 | §20, §8.2 | Review note accept/reject KG scope with rationale
D5 | P3 Architecture / G3 | D5-T1 | Artefacts 10 C4, 11 ADRs (≥10), 12 contracts | What to implement: Artefacts 10 C4, 11 ADRs (≥10), 12 contracts Expected functionality: Produce C4 views, ≥10 ADRs, contract design reconciled to evaluation/contracts schemas. Address brownfield and rollback. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P3, §12. Reviewer FDE-5 (10–12), FDE-4 (GxP claims) (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: ≥10 ADRs; 12 reconciles with evaluation/contracts/*.schema.json; brownfield/rollback addressed | FDE-3 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | G2 (D4) |  | 0% | FDE-5 (10–12), FDE-4 (GxP claims) | G3 | §8 P3, §12 | ≥10 ADRs; 12 reconciles with evaluation/contracts/*.schema.json; brownfield/rollback addressed
D5 | P3 Architecture / G3 | D5-T2 | Shared evidence-resolver (SHA-256 + source_preserved) | What to implement: Shared evidence-resolver (SHA-256 + source_preserved) Expected functionality: Implement shared resolver emitting valid evidence_item fields. Real SHA-256 (64-hex). source_preserved=true. Used by all workflows. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.3, §13. Reviewer FDE-5 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: Emits valid evidence_item fields; hash is real 64-hex; source_preserved=true | FDE-3 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D5-T1 |  | 0% | FDE-5 | G3 | §11.3, §13 | Emits valid evidence_item fields; hash is real 64-hex; source_preserved=true
D5 | P3 Architecture / G3 | D5-T3 | python -B tools/test_contracts.py green | What to implement: python -B tools/test_contracts.py green Expected functionality: Run contract tester continuously. Must show 3 positive valid and 3 negative invalid samples behaving correctly. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §4.2, §13. Reviewer FDE-5 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: 3 positive valid; 3 negative invalid | FDE-3 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D5-T1; D5-T2 |  | 0% | FDE-5 | G3 | §4.2, §13 | 3 positive valid; 3 negative invalid
D5 | P3 Architecture / G3 | D5-T4 | Draft 13–15 GxP/CSA/QRM | What to implement: Draft 13–15 GxP/CSA/QRM Expected functionality: Intended use + GxP boundary. Risk→control→test chains. Address hard-gate RUB-09. Keep AI advisory only. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P3, §12. Reviewer FDE-5 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: Intended use + GxP boundary; risks→controls→tests; hard-gate RUB-09 | FDE-4 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | Prior day exit (D4); seat capacity |  | 0% | FDE-5 | G3 | §8 P3, §12 | Intended use + GxP boundary; risks→controls→tests; hard-gate RUB-09
D5 | P3 Architecture / G3 | D5-T5 | Threat skeleton; confirm negatives still fail closed | What to implement: Threat skeleton; confirm negatives still fail closed Expected functionality: Skeleton threat model. Confirm disposition/reportability/side-effect samples still rejected by contracts. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P3. Reviewer FDE-2 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: Disposition/reportability/side-effect samples still rejected | FDE-5 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | Prior day exit (D4); seat capacity |  | 0% | FDE-2 | G3 | §8 P3 | Disposition/reportability/side-effect samples still rejected
D5 | P3 Architecture / G3 | D5-T6 | Domain rules for resolver; contract vs batch/PV facts | What to implement: Domain rules for resolver; contract vs batch/PV facts Expected functionality: Map required schema fields to evidence sources for batch and PV. No silent unit/time conversion. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §13. Reviewer FDE-3 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: Written mapping of required schema fields to sources | FDE-2 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | Prior day exit (D4); seat capacity |  | 0% | FDE-3 | G3 | §13 | Written mapping of required schema fields to sources
D5 | P3 Architecture / G3 | D5-T7 | Ops fit review of C4/ADR; ban adaptive undeclared transforms | What to implement: Ops fit review of C4/ADR; ban adaptive undeclared transforms Expected functionality: Biostats/ops lens: ban adaptive undeclared transforms. Record finding; accept in ADR or RAID. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §6.3 Biostats. Reviewer FDE-3 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: Review finding recorded; constraint accepted in ADR or RAID | FDE-1 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | Prior day exit (D4); seat capacity |  | 0% | FDE-3 | G3 | §6.3 Biostats | Review finding recorded; constraint accepted in ADR or RAID
D5 | P3 Architecture / G3 | D5-T8 | Eval step 3: create offline eval tree | What to implement: Eval step 3: create offline eval tree Expected functionality: Create submission/evaluation/{datasets,adapters,graders,policies,reports}/ + runner.py + README.md. README states brownfield→adapter→runner→graders→policies→reports. Runner stub callable. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.8 step 3, §7.2. Reviewer FDE-4 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: All seven entries exist; README states flow; runner stub callable | FDE-5 (+FDE-3) | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D3-T7; D5-T1 |  | 0% | FDE-4 | G3 | §11.8 step 3, §7.2 | All seven entries exist; README states flow; runner stub callable
D5 | P3 Architecture / G3 | D5-T9 | Policies stub: map ten release gates + hard gates | What to implement: Policies stub: map ten release gates + hard gates Expected functionality: Document/code automatic-fail rules for ten release gates and hard gates under evaluation/policies/. Each hard gate named. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.5, §11.8. Reviewer FDE-5 (author ≠ sole approver). Gate context: G3. Expected output / completion criteria: policies/ has ≥1 rule file; each hard gate named | FDE-4 (+FDE-5) | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D5-T8 |  | 0% | FDE-5 | G3 | §11.5, §11.8 | policies/ has ≥1 rule file; each hard gate named
D6 | P4 Secure design | D6-T1 | Draft 16 Threat + 17 Privacy | What to implement: Draft 16 Threat + 17 Privacy Expected functionality: Cover injection, poisoning, tool abuse, stale auth, exfil, DoW; purpose limitation. Address hard-gates RUB-10/11. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P4, §12. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Covers injection/poisoning/tool abuse/stale auth/exfil/DoW; purpose limitation; hard-gates RUB-10/11 | FDE-5 | High | Not Started | 2026-08-09 | 2026-08-09 |  | G3 (D5) |  | 0% | FDE-4 |  | §8 P4, §12 | Covers injection/poisoning/tool abuse/stale auth/exfil/DoW; purpose limitation; hard-gates RUB-10/11
D6 | P4 Secure design | D6-T2 | Write failing prohibited-action + stale-auth tests (INJ-065/066/067) | What to implement: Write failing prohibited-action + stale-auth tests (INJ-065/066/067) Expected functionality: Tests-before-inference: write failing tests for poisoned/unsigned tools and stale auth BEFORE workflow implementation. Fail for the right reason. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P4, non-negotiable #4. Reviewer FDE-3 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Tests exist before WF implementation; fail for correct reason; evidence paths set | FDE-5 | High | Not Started | 2026-08-09 | 2026-08-09 |  | D6-T1; D1-T6 |  | 0% | FDE-3 |  | §8 P4, non-negotiable #4 | Tests exist before WF implementation; fail for correct reason; evidence paths set
D6 | P4 Secure design | D6-T3 | Approved vs poisoned tool manifests; signed allowlist; no agent coding | What to implement: Approved vs poisoned tool manifests; signed allowlist; no agent coding Expected functionality: Design signed allowlist and deny path for unsigned/poisoned tools. Confirm agents still OFF (pre-G4). Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §13, agent freeze. Reviewer FDE-5 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Design denies unsigned/poisoned tools; confirmation agents still OFF | FDE-3 | High | Not Started | 2026-08-09 | 2026-08-09 |  | Prior day exit (D5); seat capacity |  | 0% | FDE-5 |  | §13, agent freeze | Design denies unsigned/poisoned tools; confirmation agents still OFF
D6 | P4 Secure design | D6-T4 | Residual risk register start; GxP impact of controls | What to implement: Residual risk register start; GxP impact of controls Expected functionality: Start residual risk list with owners. No unverified acceptance of residual GxP risk. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P4. Reviewer FDE-5 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Residual risks listed with owners; no unverified acceptance | FDE-4 | High | Not Started | 2026-08-09 | 2026-08-09 |  | Prior day exit (D5); seat capacity |  | 0% | FDE-5 |  | §8 P4 | Residual risks listed with owners; no unverified acceptance
D6 | P4 Secure design | D6-T5 | Privacy/purpose data mapping | What to implement: Privacy/purpose data mapping Expected functionality: Map consents, exports, retention conflicts for D09 injects. Support artefact 17 and privacy suite. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.1 D09. Reviewer FDE-5 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Mapping cites consents/exports/retention conflicts | FDE-2 | High | Not Started | 2026-08-09 | 2026-08-09 |  | Prior day exit (D5); seat capacity |  | 0% | FDE-5 |  | §11.1 D09 | Mapping cites consents/exports/retention conflicts
D6 | P4 Secure design | D6-T6 | HF / automation-bias notes (INJ-071) for artefact 18 | What to implement: HF / automation-bias notes (INJ-071) for artefact 18 Expected functionality: Notes on candidate_outputs and omitted-fact risk for Responsible AI artefact. Cite INJ-071. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P4. Reviewer FDE-5 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Notes cite candidate_outputs / omitted-fact risk | FDE-1 | High | Not Started | 2026-08-09 | 2026-08-09 |  | Prior day exit (D5); seat capacity |  | 0% | FDE-5 |  | §8 P4 | Notes cite candidate_outputs / omitted-fact risk
D6 | P4 Secure design | D6-T7 | Eval step 5 start: ≥3 graders with ± unit tests | What to implement: Eval step 5 start: ≥3 graders with ± unit tests Expected functionality: Implement graders for schema, prohibited actions, evidence under evaluation/graders/. Each has positive and negative unit tests. Thresholds draft until D7 freeze. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.8 step 5. Reviewer FDE-3 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Grader modules under graders/; unit tests show + and −; thresholds draft (freeze by D7) | FDE-5 | High | Not Started | 2026-08-09 | 2026-08-09 |  | D5-T8; D6-T2 |  | 0% | FDE-3 |  | §11.8 step 5 | Grader modules under graders/; unit tests show + and −; thresholds draft (freeze by D7)
D7 | P4 Secure design / G4 | D7-T1 | Draft 18 Responsible AI / human factors | What to implement: Draft 18 Responsible AI / human factors Expected functionality: Automation-bias mitigations, a11y/language risks, reviewable outputs. Uses D6 HF notes. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P4. Reviewer FDE-5 (author ≠ sole approver). Gate context: G4. Expected output / completion criteria: Automation-bias mitigations; a11y/language risks; reviewable | FDE-1 | Critical | Not Started | 2026-08-10 | 2026-08-10 |  | D6-T6 |  | 0% | FDE-5 | G4 | §8 P4 | Automation-bias mitigations; a11y/language risks; reviewable
D7 | P4 Secure design / G4 | D7-T2 | Draft 19–21 EU AI Act / ISO-aligned / assurance | What to implement: Draft 19–21 EU AI Act / ISO-aligned / assurance Expected functionality: Jurisdiction/purpose/role explicit. No certification claim. CAE/assurance skeleton for later board. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8 P4, §12. Reviewer FDE-5 (19–20), FDE-1 (21) (author ≠ sole approver). Gate context: G4. Expected output / completion criteria: Jurisdiction/purpose/role explicit; no certification claim; CAE skeleton | FDE-4 | Critical | Not Started | 2026-08-10 | 2026-08-10 |  | Prior day exit (D6); seat capacity |  | 0% | FDE-5 (19–20), FDE-1 (21) | G4 | §8 P4, §12 | Jurisdiction/purpose/role explicit; no certification claim; CAE skeleton
D7 | P4 Secure design / G4 | D7-T3 | Cursor engineering evidence in ADRs | What to implement: Cursor engineering evidence in ADRs Expected functionality: At least one ADR cites rules/skills/commands. Plan path for sample reviewer outputs under submission/evidence/. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §15. Reviewer FDE-1 (author ≠ sole approver). Gate context: G4. Expected output / completion criteria: ≥1 ADR cites rules/skills/commands; sample reviewer output path planned | FDE-3 | Critical | Not Started | 2026-08-10 | 2026-08-10 |  | Prior day exit (D6); seat capacity |  | 0% | FDE-1 | G4 | §15 | ≥1 ADR cites rules/skills/commands; sample reviewer output path planned
D7 | P4 Secure design / G4 | D7-T4 | Control↔test map; every hard-gate threat has failing test | What to implement: Control↔test map; every hard-gate threat has failing test Expected functionality: Traceability table: threat → test → expected fail. Required for G4. No missing critical control. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §8.2 G4. Reviewer FDE-3 (author ≠ sole approver). Gate context: G4. Expected output / completion criteria: Traceability table threat→test→expected fail; no missing critical control | FDE-5 | Critical | Not Started | 2026-08-10 | 2026-08-10 |  | D6-T2; D6-T1 |  | 0% | FDE-3 | G4 | §8.2 G4 | Traceability table threat→test→expected fail; no missing critical control
D7 | P4 Secure design / G4 | D7-T5 | Cross-check assurance claims vs evidence register | What to implement: Cross-check assurance claims vs evidence register Expected functionality: Every assurance claim must point to a register evidence path. Remove or downgrade unsupported claims. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11. Reviewer FDE-4 (author ≠ sole approver). Gate context: G4. Expected output / completion criteria: No claim without register evidence path | FDE-2 | Critical | Not Started | 2026-08-10 | 2026-08-10 |  | Prior day exit (D6); seat capacity |  | 0% | FDE-4 | G4 | §11 | No claim without register evidence path
D7 | P4 Secure design / G4 | D7-T6 | Freeze grader/suite thresholds before improved-system results | What to implement: Freeze grader/suite thresholds before improved-system results Expected functionality: Commit thresholds in decision log before seeing improved submission/src results. No post-hoc softening without RAID (R-007). Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS. FINAL ref §11.8, R-007. Reviewer FDE-4 (author ≠ sole approver). Gate context: G4. Expected output / completion criteria: Threshold commit date/version logged; no post-hoc softening without RAID | FDE-5 | Critical | Not Started | 2026-08-10 | 2026-08-10 |  | D6-T7; D5-T9 |  | 0% | FDE-4 | G4 | §11.8, R-007 | Threshold commit date/version logged; no post-hoc softening without RAID
D8 | P5 POC build | D8-T1 | Shared resolver + Workflow A + app shell | What to implement: Shared resolver + Workflow A + app shell Expected functionality: Implement WF-A batch advisory path + app shell. readiness_state enum only; no disposition fields. App uses text nodes — no innerHTML. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §13, §12 RUB-08. Reviewer FDE-5 (+ FDE-4 GxP) (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Schema-valid batch responses; readiness_state enum only; no disposition fields; no innerHTML | FDE-3 | High | Not Started | 2026-08-11 | 2026-08-11 |  | G4 (D7); D5-T2; D6-T2 |  | 0% | FDE-5 (+ FDE-4 GxP) |  | §13, §12 RUB-08 | Schema-valid batch responses; readiness_state enum only; no disposition fields; no innerHTML
D8 | P5 POC build | D8-T2 | Start Workflow C (draft options) | What to implement: Start Workflow C (draft options) Expected functionality: Begin supply/clinical options workflow. All options status=draft; no_side_effects=true on success and error paths. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §13. Reviewer FDE-5 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Options status=draft; no_side_effects=true on success/error paths | FDE-3 | High | Not Started | 2026-08-11 | 2026-08-11 |  | D8-T1 |  | 0% | FDE-5 |  | §13 | Options status=draft; no_side_effects=true on success/error paths
D8 | P5 POC build | D8-T3 | WF-A domain rules + sign-off criteria | What to implement: WF-A domain rules + sign-off criteria Expected functionality: Written batch domain rules and sign-off checklist forbidding release/reject/recall language. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §6.4, §13. Reviewer FDE-3 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Written rules; sign-off checklist forbids release/reject/recall language | FDE-4 | High | Not Started | 2026-08-11 | 2026-08-11 |  | Prior day exit (D7); seat capacity |  | 0% | FDE-3 |  | §6.4, §13 | Written rules; sign-off checklist forbids release/reject/recall language
D8 | P5 POC build | D8-T4 | WF-C domain rules (ethics, approvals_required) | What to implement: WF-C domain rules (ethics, approvals_required) Expected functionality: Rules for WF-C: no reserve/allocate/ship verbs; named approvals_required; ethics constraints explicit. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §6.4, §13. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: No reserve/allocate/ship verbs in outputs; approvals named | FDE-1 | High | Not Started | 2026-08-11 | 2026-08-11 |  | Prior day exit (D7); seat capacity |  | 0% | FDE-4 |  | §6.4, §13 | No reserve/allocate/ship verbs in outputs; approvals named
D8 | P5 POC build | D8-T5 | Batch/PV domain rules; verbatim preservation for B | What to implement: Batch/PV domain rules; verbatim preservation for B Expected functionality: Prepare WF-B rules: source_facts, clocks, listedness, required_reviews preserved verbatim. No final safety conclusions. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §13. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Rules require source_facts/clocks/listedness fields preserved | FDE-2 | High | Not Started | 2026-08-11 | 2026-08-11 |  | Prior day exit (D7); seat capacity |  | 0% | FDE-4 |  | §13 | Rules require source_facts/clocks/listedness fields preserved
D8 | P5 POC build | D8-T6 | Tests for A + authz-at-execution; execution_status=not_executed | What to implement: Tests for A + authz-at-execution; execution_status=not_executed Expected functionality: Tests for WF-A allow path and deny on revoked/stale cache (INJ-067). Contracts still 3+/3−. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §13, INJ-067. Reviewer FDE-4 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Allow path passes; deny on revoked/stale cache; contracts still 3+/3− | FDE-5 | High | Not Started | 2026-08-11 | 2026-08-11 |  | Prior day exit (D7); seat capacity |  | 0% | FDE-4 |  | §13, INJ-067 | Allow path passes; deny on revoked/stale cache; contracts still 3+/3−
D8 | P5 POC build | D8-T7 | Eval step 4: build adapter | What to implement: Eval step 4: build adapter Expected functionality: Adapter under evaluation/adapters/ captures input, output, evidence, tools, retries, errors, approvals, side effects, latency. Wire WF-A; C/B stubs OK. No silent side effects. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.8 step 4. Reviewer FDE-5 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: Adapter under adapters/; wired for WF-A; no silent side effects | FDE-3 | High | Not Started | 2026-08-11 | 2026-08-11 |  | D5-T8; D8-T1 |  | 0% | FDE-5 |  | §11.8 step 4 | Adapter under adapters/; wired for WF-A; no silent side effects
D8 | P5 POC build | D8-T8 | Eval step 6 baseline: run suite on unmodified starter/ | What to implement: Eval step 6 baseline: run suite on unmodified starter/ Expected functionality: Run eval against unmodified brownfield starter/. Write reports/baseline/summary.json and failed_cases.json (or document gaps). Gaps drive improvement backlog. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.8 step 6, M6b. Reviewer FDE-3 (author ≠ sole approver). Gate context: day exit / phase checkpoint. Expected output / completion criteria: reports/baseline/ has summary.json + failed_cases.json (or documented gaps); gaps drive backlog | FDE-5 | High | Not Started | 2026-08-11 | 2026-08-11 |  | D8-T7; D6-T7 |  | 0% | FDE-3 |  | §11.8 step 6, M6b | reports/baseline/ has summary.json + failed_cases.json (or documented gaps); gaps drive backlog
D9 | P5 POC build / G5 | D9-T1 | Finish WF-C then WF-B; AI-disabled path + scripts | What to implement: Finish WF-C then WF-B; AI-disabled path + scripts Expected functionality: Respect build order A→C→B. Finish C then B. AI-disabled path produces schema-valid outputs. Document scripts. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §13, §8 P5. Reviewer FDE-5 (author ≠ sole approver). Gate context: G5. Expected output / completion criteria: Build order respected; AI-off schema-valid; scripts documented | FDE-3 | Critical | Not Started | 2026-08-12 | 2026-08-12 |  | D8-T1; D8-T2 |  | 0% | FDE-5 | G5 | §13, §8 P5 | Build order respected; AI-off schema-valid; scripts documented
D9 | P5 POC build / G5 | D9-T2 | Finalize WF-C options + demo narrative | What to implement: Finalize WF-C options + demo narrative Expected functionality: Demo script shows draft-only options and constraint violations. No shipment/allocation language. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §6.4. Reviewer FDE-4 (author ≠ sole approver). Gate context: G5. Expected output / completion criteria: Demo script shows draft-only options + constraint violations | FDE-1 | Critical | Not Started | 2026-08-12 | 2026-08-12 |  | Prior day exit (D8); seat capacity |  | 0% | FDE-4 | G5 | §6.4 | Demo script shows draft-only options + constraint violations
D9 | P5 POC build / G5 | D9-T3 | Finalize WF-B domain (duplicates/clocks/listedness/reviews) | What to implement: Finalize WF-B domain (duplicates/clocks/listedness/reviews) Expected functionality: Populate required PV fields; both MedDRA versions / listedness_context as required; never emit final safety conclusions. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.3 PV. Reviewer FDE-4 (author ≠ sole approver). Gate context: G5. Expected output / completion criteria: Required PV fields populated; no final safety conclusions | FDE-2 | Critical | Not Started | 2026-08-12 | 2026-08-12 |  | Prior day exit (D8); seat capacity |  | 0% | FDE-4 | G5 | §11.3 PV | Required PV fields populated; no final safety conclusions
D9 | P5 POC build / G5 | D9-T4 | Dual PV sign-off with FDE-2; no final safety fields | What to implement: Dual PV sign-off with FDE-2; no final safety fields Expected functionality: Joint sign record with FDE-2. Schema scan confirms no prohibited final-safety properties. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §6.4. Reviewer FDE-5 (author ≠ sole approver). Gate context: G5. Expected output / completion criteria: Joint sign record; schema scan shows no prohibited properties | FDE-4 | Critical | Not Started | 2026-08-12 | 2026-08-12 |  | Prior day exit (D8); seat capacity |  | 0% | FDE-5 | G5 | §6.4 | Joint sign record; schema scan shows no prohibited properties
D9 | P5 POC build / G5 | D9-T5 | Prohibited-action suite fail-closed; subgroup smoke | What to implement: Prohibited-action suite fail-closed; subgroup smoke Expected functionality: Negatives fail closed. Demonstrate ≥1 abstain path. Wire graders into runner for G5 evidence. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.5, §8.2 G5. Reviewer FDE-3 (author ≠ sole approver). Gate context: G5. Expected output / completion criteria: Negatives fail; at least one abstain path demonstrated | FDE-5 | Critical | Not Started | 2026-08-12 | 2026-08-12 |  | D6-T2; D9-T1 |  | 0% | FDE-3 | G5 | §11.5, §8.2 G5 | Negatives fail; at least one abstain path demonstrated
D9 | P5 POC build / G5 | D9-T6 | MVP demo pack (happy + abstain) | What to implement: MVP demo pack (happy + abstain) Expected functionality: Recorded run with scenario IDs, input hashes, reviewer, gate outcome fields. Happy path + abstain path. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.2 G5, M5. Reviewer FDE-1 facilitates (author ≠ sole approver). Gate context: G5. Expected output / completion criteria: Recorded run: scenario IDs, hashes, reviewer, gate outcome fields ready | All | Critical | Not Started | 2026-08-12 | 2026-08-12 |  | D9-T1; D9-T2; D9-T3 |  | 0% | FDE-1 facilitates | G5 | §8.2 G5, M5 | Recorded run: scenario IDs, hashes, reviewer, gate outcome fields ready
D10 | P6–P8 TEVV / Ops / Defence | D10-T1 | Artefacts 22–25; 12 suites via runner+graders+policies; red-team/outage | What to implement: Artefacts 22–25; 12 suites via runner+graders+policies; red-team/outage Expected functionality: Complete eval/reliability/incident artefacts. Run 12 suites through full eval stack. Pre-committed thresholds. ≥1 failed-gate demo. Policies auto-fail hard gates. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8 P6, §11.4–11.5, §11.8. Reviewer FDE-4 (22,24,25), FDE-3 (outage) (author ≠ sole approver). Gate context: G6. Expected output / completion criteria: All 12 suites have evidence; thresholds pre-committed; ≥1 failed-gate demo; policies auto-fail on hard gates | FDE-5 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | G5 (D9); D7-T6 |  | 0% | FDE-4 (22,24,25), FDE-3 (outage) | G6 | §8 P6, §11.4–11.5, §11.8 | All 12 suites have evidence; thresholds pre-committed; ≥1 failed-gate demo; policies auto-fail on hard gates
D10 | P6–P8 TEVV / Ops / Defence | D10-T2 | Write test_results.json + evaluation_results.json | What to implement: Write test_results.json + evaluation_results.json Expected functionality: Package evidence files per SUBMISSION_EVIDENCE_STANDARD. Stable relative paths. Valid JSON. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §7.2, SUBMISSION_EVIDENCE_STANDARD. Reviewer FDE-3 (author ≠ sole approver). Gate context: G6. Expected output / completion criteria: Required fields present; JSON parses; paths relative/stable | FDE-5 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D10-T1 |  | 0% | FDE-3 | G6 | §7.2, SUBMISSION_EVIDENCE_STANDARD | Required fields present; JSON parses; paths relative/stable
D10 | P6–P8 TEVV / Ops / Defence | D10-T3 | Artefacts 23/26/29/30; fold delivery FinOps into 23 | What to implement: Artefacts 23/26/29/30; fold delivery FinOps into 23 Expected functionality: FinOps (23) includes human review cost and cites finops_delivery_log.csv. TOM (26), roadmap (29), pitch (30). Recommendation enum draft. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8 P6–P8, §11.9, §12. Reviewer FDE-5 (23), FDE-4 (26/29/30) (author ≠ sole approver). Gate context: G6–G8. Expected output / completion criteria: Cost includes human review; delivery FinOps log cited; pitch has residual risk; recommendation enum set | FDE-1 | High | Not Started | 2026-08-13 | 2026-08-13 |  | Prior day exit (D9); seat capacity |  | 0% | FDE-5 (23), FDE-4 (26/29/30) | G6–G8 | §8 P6–P8, §11.9, §12 | Cost includes human review; delivery FinOps log cited; pitch has residual risk; recommendation enum set
D10 | P6–P8 TEVV / Ops / Defence | D10-T4 | Subgroup/multilingual evidence; inspection support; PV suites | What to implement: Subgroup/multilingual evidence; inspection support; PV suites Expected functionality: Subgroup gaps explicit. Inspection path to immutable challenge evidence. Support PV evaluation suites. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.4 #7/#10. Reviewer FDE-5 (author ≠ sole approver). Gate context: G6. Expected output / completion criteria: Subgroup gaps explicit; inspection path to immutable evidence | FDE-2 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | Prior day exit (D9); seat capacity |  | 0% | FDE-5 | G6 | §11.4 #7/#10 | Subgroup gaps explicit; inspection path to immutable evidence
D10 | P6–P8 TEVV / Ops / Defence | D10-T5 | Clean-room; finalize scripts; freeze; hash; --final | What to implement: Clean-room; finalize scripts; freeze; hash; --final Expected functionality: Execute clean-room (§18). Finalize setup/run/test/evaluate/reset. Freeze, hash_submission --check, check_submission_structure --final. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §4.3, §18, §19. Reviewer Outsider + FDE-5 (author ≠ sole approver). Gate context: G7. Expected output / completion criteria: Preflight×2; scripts complete; --check PASS; --final PASS | FDE-3 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D10-T1; D10-T2 |  | 0% | Outsider + FDE-5 | G7 | §4.3, §18, §19 | Preflight×2; scripts complete; --check PASS; --final PASS
D10 | P6–P8 TEVV / Ops / Defence | D10-T6 | Inspection drill; residual risk; defence 4/5/11; 27 vendor exit | What to implement: Inspection drill; residual risk; defence 4/5/11; 27 vendor exit Expected functionality: Run inspection drill. Update residual risk. Draft artefact 27 (vendor exit) for RUB-15. Prep defence elements 4/5/11. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.6, §12. Reviewer FDE-5 (author ≠ sole approver). Gate context: G7–G8. Expected output / completion criteria: Drill record; 27 hard-gate RUB-15 addressed | FDE-4 | High | Not Started | 2026-08-13 | 2026-08-13 |  | Prior day exit (D9); seat capacity |  | 0% | FDE-5 | G7–G8 | §11.6, §12 | Drill record; 27 hard-gate RUB-15 addressed
D10 | P6–P8 TEVV / Ops / Defence | D10-T7 | Rehearse 13 defence elements; board recommendation | What to implement: Rehearse 13 defence elements; board recommendation Expected functionality: Name presenter per defence element. Record go/conditional/pivot/pause/stop recommendation. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.6, §8.2 G8. Reviewer Full team (author ≠ sole approver). Gate context: G8. Expected output / completion criteria: Named presenter per element; recommendation recorded | All | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | Prior day exit (D9); seat capacity |  | 0% | Full team | G8 | §11.6, §8.2 G8 | Named presenter per element; recommendation recorded
D10 | P6–P8 TEVV / Ops / Defence | D10-T8 | Eval step 6 reports: full report set vs baseline | What to implement: Eval step 6 reports: full report set vs baseline Expected functionality: Emit summary.json, detailed_results.jsonl, scorecard.csv, failed_cases.json, final_evaluation_report.md under evaluation/reports/. Call out baseline vs improved. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.8 reports. Reviewer FDE-2 (author ≠ sole approver). Gate context: G6. Expected output / completion criteria: Full report set present; baseline comparison called out | FDE-5 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D8-T8; D10-T1 |  | 0% | FDE-2 | G6 | §11.8 reports | Full report set present; baseline comparison called out
D10 | P6–P8 TEVV / Ops / Defence | D10-T9 | Close FinOps delivery log through D10; efficiency summary | What to implement: Close FinOps delivery log through D10; efficiency summary Expected functionality: Ensure all Track-A days have FinOps rows. Write summary (sessions/iterations/suite runs → outcomes) for artefact 23 and defence element 9. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §11.9. Reviewer FDE-5 (author ≠ sole approver). Gate context: G6–G8. Expected output / completion criteria: All Track-A days have rows; summary paragraph for artefact 23 / defence element 9 | FDE-1 | High | Not Started | 2026-08-13 | 2026-08-13 |  | D1-T9; D10-T3 |  | 0% | FDE-5 | G6–G8 | §11.9 | All Track-A days have rows; summary paragraph for artefact 23 / defence element 9
D11 | P9 Hardening | D11-T1 | App packaging & config; versioned RC; locked deps | What to implement: App packaging & config; versioned RC; locked deps Expected functionality: Package app for RC. Version ID + lockfile or stdlib mode documented. Track B only. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-5 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: RC version ID; lockfile/stdlib mode documented | FDE-3 | High | Not Started | 2026-08-14 | 2026-08-14 |  | G8 (D10) |  | 0% | FDE-5 | P9 | §8.1 | RC version ID; lockfile/stdlib mode documented
D11 | P9 Hardening | D11-T2 | Observability & SLOs / error budget | What to implement: Observability & SLOs / error budget Expected functionality: Define metrics/logs and error budget against G1 NFRs. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Metrics/logs defined; error budget stated | FDE-5+FDE-3 | High | Not Started | 2026-08-14 | 2026-08-14 |  | Prior day exit (D10); seat capacity |  | 0% | FDE-4 | P9 | §8.1 | Metrics/logs defined; error budget stated
D11 | P9 Hardening | D11-T3 | Support runbooks (OPS, AI-disabled, kill switch) | What to implement: Support runbooks (OPS, AI-disabled, kill switch) Expected functionality: Complete OPERATIONS and AI_DISABLED runbooks with prerequisites, I/O, failure, rollback, kill switch. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1, §7.2. Reviewer FDE-3 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Prerequisites/IO/failure/rollback sections present | FDE-1+FDE-5 | High | Not Started | 2026-08-14 | 2026-08-14 |  | Prior day exit (D10); seat capacity |  | 0% | FDE-3 | P9 | §8.1, §7.2 | Prerequisites/IO/failure/rollback sections present
D11 | P9 Hardening | D11-T4 | Accessibility smoke; readiness gaps for 28 | What to implement: Accessibility smoke; readiness gaps for 28 Expected functionality: Keyboard critical-path smoke. Log gaps into readiness artefact 28 backlog. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-5 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Keyboard critical-path result logged | FDE-4+FDE-1 | High | Not Started | 2026-08-14 | 2026-08-14 |  | Prior day exit (D10); seat capacity |  | 0% | FDE-5 | P9 | §8.1 | Keyboard critical-path result logged
D11 | P9 Hardening | D11-T5 | Domain regression checklist on RC | What to implement: Domain regression checklist on RC Expected functionality: Checklist covering A/B/C boundary regressions for RC sign-off. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1 / owes. Reviewer FDE-4 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Checklist covers A/B/C boundary regressions | FDE-2 | High | Not Started | 2026-08-14 | 2026-08-14 |  | Prior day exit (D10); seat capacity |  | 0% | FDE-4 | P9 | §8.1 / owes | Checklist covers A/B/C boundary regressions
D12 | P9 Hardening | D12-T1 | Security retest on RC | What to implement: Security retest on RC Expected functionality: Re-execute critical threat controls on RC build. Log PASS/FAIL. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Critical threat controls re-executed on RC; PASS/FAIL logged | FDE-5 | High | Not Started | 2026-08-15 | 2026-08-15 |  | D11-T1 |  | 0% | FDE-4 | P9 | §8.1 | Critical threat controls re-executed on RC; PASS/FAIL logged
D12 | P9 Hardening | D12-T2 | Backup/restore + rollback; RTO/RPO evidence | What to implement: Backup/restore + rollback; RTO/RPO evidence Expected functionality: Restore drill with evidence path. Record RTO/RPO numbers vs NFRs. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Restore drill evidence path; RTO/RPO numbers recorded | FDE-3+FDE-5 | High | Not Started | 2026-08-15 | 2026-08-15 |  | Prior day exit (D11); seat capacity |  | 0% | FDE-4 | P9 | §8.1 | Restore drill evidence path; RTO/RPO numbers recorded
D12 | P9 Hardening | D12-T3 | Performance/budget soak | What to implement: Performance/budget soak Expected functionality: Soak against declared NFR/FinOps budgets. CONDITIONAL requires RAID. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-1 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Within declared NFR/FinOps budgets or CONDITIONAL with RAID | FDE-5 | High | Not Started | 2026-08-15 | 2026-08-15 |  | Prior day exit (D11); seat capacity |  | 0% | FDE-1 | P9 | §8.1 | Within declared NFR/FinOps budgets or CONDITIONAL with RAID
D12 | P9 Hardening | D12-T4 | TOM support tiers; release decision prep | What to implement: TOM support tiers; release decision prep Expected functionality: Name L1/L2/L3 support. Prepare release decision template for G9. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: L1/L2/L3 named; release decision template ready | FDE-1 | High | Not Started | 2026-08-15 | 2026-08-15 |  | Prior day exit (D11); seat capacity |  | 0% | FDE-4 | P9 | §8.1 | L1/L2/L3 named; release decision template ready
D12 | P9 Hardening | D12-T5 | RC domain regression sign-off | What to implement: RC domain regression sign-off Expected functionality: Sign that no A/B/C boundary regression on RC. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref owes G9. Reviewer FDE-4 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Sign record: no boundary regression | FDE-2 | High | Not Started | 2026-08-15 | 2026-08-15 |  | Prior day exit (D11); seat capacity |  | 0% | FDE-4 | P9 | owes G9 | Sign record: no boundary regression
D12 | P9 Hardening | D12-T6 | Residual risk update for board | What to implement: Residual risk update for board Expected functionality: Refresh residual risk list for Readiness Board; acceptance pending board. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1 G9. Reviewer FDE-5 (author ≠ sole approver). Gate context: P9. Expected output / completion criteria: Residual risk list current; acceptance pending board | FDE-4 | High | Not Started | 2026-08-15 | 2026-08-15 |  | Prior day exit (D11); seat capacity |  | 0% | FDE-5 | P9 | §8.1 G9 | Residual risk list current; acceptance pending board
D13 | P9 Readiness / G9 | D13-T1 | Chair Production Readiness Board (artefact 28) | What to implement: Chair Production Readiness Board (artefact 28) Expected functionality: Chair G9 board. Blockers=0 or No-Go. Minutes recorded. No prod-ready language without PASS. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1, §8.2 G9. Reviewer Board (all) (author ≠ sole approver). Gate context: G9. Expected output / completion criteria: Blockers=0 or No-Go; minutes recorded | FDE-4 | Critical | Not Started | 2026-08-16 | 2026-08-16 |  | D12-T6; D12-T1 |  | 0% | Board (all) | G9 | §8.1, §8.2 G9 | Blockers=0 or No-Go; minutes recorded
D13 | P9 Readiness / G9 | D13-T2 | RC tag + manifest; clean-room on RC | What to implement: RC tag + manifest; clean-room on RC Expected functionality: Immutable RC tag + manifest. Repeat clean-room on RC extract. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer Outsider + FDE-5 (author ≠ sole approver). Gate context: G9. Expected output / completion criteria: Tag immutable; RC clean-room PASS | FDE-3 | Critical | Not Started | 2026-08-16 | 2026-08-16 |  | D11-T1; D10-T5 |  | 0% | Outsider + FDE-5 | G9 | §8.1 | Tag immutable; RC clean-room PASS
D13 | P9 Readiness / G9 | D13-T3 | Release decision sign; G9 minutes | What to implement: Release decision sign; G9 minutes Expected functionality: Signed go/no-go. If No-Go, no production-ready language in materials. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: G9. Expected output / completion criteria: Signed go/no-go; no prod-ready language if No-Go | FDE-1 | Critical | Not Started | 2026-08-16 | 2026-08-16 |  | Prior day exit (D12); seat capacity |  | 0% | FDE-4 | G9 | §8.1 | Signed go/no-go; no prod-ready language if No-Go
D13 | P9 Readiness / G9 | D13-T4 | Security sign at G9 | What to implement: Security sign at G9 Expected functionality: Written security sign referencing RC retest evidence. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §8.1. Reviewer FDE-4 (author ≠ sole approver). Gate context: G9. Expected output / completion criteria: Written sec sign referencing RC retest | FDE-5 | Critical | Not Started | 2026-08-16 | 2026-08-16 |  | Prior day exit (D12); seat capacity |  | 0% | FDE-4 | G9 | §8.1 | Written sec sign referencing RC retest
D13 | P9 Readiness / G9 | D13-T5 | Domain sign at board | What to implement: Domain sign at board Expected functionality: Written domain sign for board that boundary obligations hold on RC. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref owes G9. Reviewer FDE-4 (author ≠ sole approver). Gate context: G9. Expected output / completion criteria: Written domain sign | FDE-2 | Critical | Not Started | 2026-08-16 | 2026-08-16 |  | Prior day exit (D12); seat capacity |  | 0% | FDE-4 | G9 | owes G9 | Written domain sign
D14 | Buffer | D14-T* | Buffer / defect burn-down | What to implement: Buffer / defect burn-down Expected functionality: Close defects or defer with RAID. Keep defence pack stable. Optional Track A polish only. Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents may be used only after G4 PASS; still no prohibited autonomy. FINAL ref §5.4. Reviewer Stream backups (author ≠ sole approver). Gate context: Buffer. Expected output / completion criteria: Defects closed or deferred with RAID; defence pack stable | All | Medium | Not Started | 2026-08-17 | 2026-08-17 |  | Prior day exit (D13); seat capacity |  | 0% | Stream backups | Buffer | §5.4 | Defects closed or deferred with RAID; defence pack stable

## By_Day
Day | Task count | Not Started | In Progress | Blocked | Completed | On Hold | Avg completion
D1 | 9
D2 | 7
D3 | 7
D4 | 6
D5 | 9
D6 | 7
D7 | 6
D8 | 8
D9 | 6
D10 | 9
D11 | 5
D12 | 6
D13 | 5
D14 | 1

## Gate_Board
Gate | Day | Evaluation question | Reviewers | Pass criteria | Gate result | Notes
Preflight | D1 | Package integrity baseline + team ready? | Full team | Hour-0 PASS archived; seats named; FINAL ratified; --scaffold PASS
G1 | D2 | Problem measurable; no-AI honest; NFRs locked? | FDE-4 + FDE-5 | 01–04 drafted with citations; no-AI table present; NFR table locked; stop/pivot stated
G2 | D4 | Conflicts tracked not silently resolved; inject register real? | FDE-1 + FDE-4 | Conflict list exists; register 84 rows ≠ silent delete; no cleaned units/IDs
G3 | D5 | Prohibited actions outside executable boundary? | FDE-2 + FDE-5 | test_contracts 3+/3−; design forbids disposition/reportability/side effects
G4 | D7 | Threat/privacy/ISO controls + failing prohibited tests exist? | FDE-1 + FDE-3 | 16–21 drafted; prohibited/stale-auth tests fail for right reason before WF code
G5 | D9 | Three workflows run offline against fixtures? | FDE-1 + FDE-4 | A/B/C offline; schema-valid; demo happy + abstain; AI-disabled path shown
G6 | D10 | Red-team / outage / cost gates fail closed as designed? | FDE-2 + FDE-3 | Suites evidence; failed-gate demo; thresholds pre-committed
G7 | D10 | Clean-room + --final + hash --check? | Full team + outsider | Clean extract succeeds; hashes match; --final PASS
G8 | D10 | 13 defence elements rehearsed; recommendation clear? | Full team | Presenters named; go/conditional/pivot/pause/stop recorded
G9 | D13 | Readiness Board; Blockers=0; RC clean-room? | FDE-4 chairs | 28 complete; hard gates on RC; RC clean-room; P1/P4/P5 signs