## Instructions
AEGIS FDE Day-wise Task Tracker V2 (5-member team)
Source of truth: AEGIS_PROJECT_PLAN_V2.md + AEGIS_FDE_DAYWISE_TASK_DISTRIBUTION.md
Regenerate: python -B ProjectPlan/_build_daywise_tracker_v2.py
Supersedes: AEGIS_FDE_DAYWISE_TASK_TRACKER.xlsx (v1)
Seats: P1 Product/Value · P2 Domain/Evidence · P3 Architecture/Build · P4 GxP/ISO · P5 Security/Eval
Aliases: P1…P5 ≡ FDE-1…5
Columns: Date/Day · Module · Task ID · Task · Task Details · Assigned To · Priority · Status ·
Start / Expected / Actual · Dependencies · Blockers · Completion % · Reviewer · Gate · Plan V2 ref ·
Evaluation criteria · Result · Evidence path
Dropdowns — Priority: Low¦Medium¦High¦Critical
Status: Not Started¦In Progress¦Blocked¦Completed¦On Hold
Result: PASS¦FAIL¦CONDITIONAL¦N/A
Rules: author ≠ sole approver · Agents OFF until G4 · work under submission/ only · Plan V2 SoT
Continuity: batch & supply max_ai_outage_days=14; PV max_ai_outage_hours=0
Hard gates apply independently of 180-pt score
Evidence-export is Must (DoD) in addition to five name-matched scripts
Calendar: D1 = 2026-08-05 (Option B+ sequential session days; adjust at kickoff)
Validated Task Details for all 96 tasks against Plan V2 (G-24…G-38 closures).

## Task_Tracker
Date / Day | Module / Workstream | Task ID | Task | Task Details | Assigned To | Priority | Status | Start Date | Expected Completion Date | Actual Completion Date | Dependencies | Blockers / Remarks | Completion Percentage | Reviewer | Gate | Plan V2 ref | Evaluation criteria | Result | Evidence path
D1 | P0 Preflight | D1-T1 | Hour-0 preflight; archive VALIDATION_REPORT.json | What to implement: Hour-0 preflight; archive VALIDATION_REPORT.json / Expected functionality: Run `python -B run_capstone.py --check` once. Archive VALIDATION_REPORT.json under submission/evidence/ with timestamp. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: python -B; PASS archived under submission/evidence/ | P3 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | Kickoff |  | 0% | P5 | Preflight | §4.2, §8 P0 | python -B; PASS archived under submission/evidence/
D1 | P0 Preflight | D1-T2 | Scaffold submission dirs; -B convention | What to implement: Scaffold submission dirs; -B convention / Expected functionality: Create submission tree via check_submission_structure.py --scaffold. Document python -B for all commands. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: --scaffold PASS; required dirs exist | P3 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | Kickoff |  | 0% | P1 | Preflight | §7.2, §8 P0 | --scaffold PASS; required dirs exist
D1 | P0 Preflight | D1-T3 | Team charter + SCQA; open Assumptions/Decision/RAID logs | What to implement: Team charter + SCQA; open Assumptions/Decision/RAID logs / Expected functionality: Charter with SCQA, seats P1–P5, prohibited AI actions, dual-track honesty. Create logs under submission/evidence/. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Charter + three logs; seats named; dual-track stated | P1 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | Kickoff |  | 0% | P4 | Preflight | §8 P0, §17, §21 | Charter + three logs; seats named; dual-track stated
D1 | P0 Preflight | D1-T4 | Case + inject catalogue skim; deliberate ambiguity preserved | What to implement: Case + inject catalogue skim; deliberate ambiguity preserved / Expected functionality: Read INTEGRATED_CASE + injects. Hotspot list D01–D13. Do not clean conflicts (constraint 11). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Hotspot list; no conflict 'fixes' | P2 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | Kickoff |  | 0% | P3 | Preflight | §3, constraint 11 | Hotspot list; no conflict 'fixes'
D1 | P0 Preflight | D1-T5 | Prohibited-action catalogue (ai_use_boundaries + decision_rights) | What to implement: Prohibited-action catalogue (ai_use_boundaries + decision_rights) / Expected functionality: Map forbids to WF A/B/C from challenge CSVs. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Catalogue maps A/B/C forbids; cites CSV paths | P4 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | Kickoff |  | 0% | P5 | Preflight | §1, §3.2 | Catalogue maps A/B/C forbids; cites CSV paths
D1 | P0 Preflight | D1-T6 | Security/privacy stop lines; INJ-065/066/067 | What to implement: Security/privacy stop lines; INJ-065/066/067 / Expected functionality: Deny-by-default stop lines for poisoned/unsigned tools and stale auth. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Stop lines + three inject IDs | P5 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | Kickoff |  | 0% | P4 | Preflight | §3.4, §11 | Stop lines + three inject IDs
D1 | P0 Preflight | D1-T7 | Ratify AEGIS_PROJECT_PLAN_V2.md | What to implement: Ratify AEGIS_PROJECT_PLAN_V2.md / Expected functionality: Decision-log: V2.0 is governing SoT; FINAL superseded; dual-track honesty; G9 optional for score. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Decision-log entry: V2 ratified + date | All | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T1; D1-T2; D1-T3 |  | 0% | P1 records | Preflight | §21, document control | Decision-log entry: V2 ratified + date
D1 | P0 Preflight | D1-T8 | Eval step 1: brownfield understanding note | What to implement: Eval step 1: brownfield understanding note / Expected functionality: Document workflows/I/O/evidence/tools/rules/tests/failure/approval. Cite starter/ + contracts. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Note covers eight topics; cites starter/contracts | P5 (+P3) | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T4 |  | 0% | P2 | Preflight | §11.8 step 1 | Note covers eight topics; cites starter/contracts
D1 | P0 Preflight | D1-T9 | Create finops_delivery_log.csv; seed D1 rows | What to implement: Create finops_delivery_log.csv; seed D1 rows / Expected functionality: Create submission/evidence/finops_delivery_log.csv with V2 §11.9 header: date,stage_or_task,owner,chat_sessions,files_attached,agent_iterations,terminal_commands,files_modified,failed_attempts,full_suite_runs,outcome,notes. Each seat ≥1 D1 row; agent_iterations=0 until G4. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Header matches §11.9; each seat ≥1 D1 row | P1 | Critical | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T3 |  | 0% | P5 | Preflight | §11.9 | Header matches §11.9; each seat ≥1 D1 row
D1 | P0 Preflight | D1-T10 | Confirm Cursor roots + operating method | What to implement: Confirm Cursor roots + operating method / Expected functionality: Confirm always-on pharma-fde.mdc + engineering-principles.mdc. Record Plan Mode first / one-stage-per-run / fresh-chat rules (§15.1). No root AGENTS.md duplicate. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Decision-log cites both rules + §15.1 session discipline | P3 | High | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T7 |  | 0% | P5 | Preflight | §15, §15.1, constraint 15 | Decision-log cites both rules + §15.1 session discipline
D1 | P0 Preflight | D1-T11 | Mirror ProjectPlan SoT into submission/artefacts/ProjectPlan/ | What to implement: Mirror ProjectPlan SoT into submission/artefacts/ProjectPlan/ / Expected functionality: Copy V2 plan, daywise MD, tracker V2, timeline PNG into submission mirror path. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Mirror paths exist under submission/artefacts/ProjectPlan/ | P3 | High | Not Started | 2026-08-05 | 2026-08-05 |  | D1-T2; D1-T7 |  | 0% | P1 | Preflight | document control; §21 | Mirror paths exist under submission/artefacts/ProjectPlan/
D2 | P1 Discovery / G1 | D2-T1 | Draft artefacts 01–04 | What to implement: Draft artefacts 01–04 / Expected functionality: Problem/value, business case, stakeholders, AI blueprint. Cite BR-01, kpi_conflicts, stakeholders, ai_use_boundaries. FACT/ASSUMPTION labels. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Citations + labels; substantive length | P1 | Critical | Not Started | 2026-08-06 | 2026-08-06 |  | D1-T7 |  | 0% | P4 (01–03), P5 (04) | G1 | §8 P1, §12 | Citations + labels; substantive length
D2 | P1 Discovery / G1 | D2-T2 | No-AI comparison + stop/pivot | What to implement: No-AI comparison + stop/pivot / Expected functionality: master_data_repair vs rules vs GenAI; stop/pivot/pause/abstain including prohibited autonomy. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Comparison table + stop triggers | P1 | Critical | Not Started | 2026-08-06 | 2026-08-06 |  | D2-T1 |  | 0% | P5 | G1 | §3.3, §3.4 | Comparison table + stop triggers
D2 | P1 Discovery / G1 | D2-T3 | Lock production NFRs @ G1 | What to implement: Lock production NFRs @ G1 / Expected functionality: Fill 8 NFR rows; no certification overclaim. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: All 8 NFR rows locked | P1 | Critical | Not Started | 2026-08-06 | 2026-08-06 |  | D2-T1 |  | 0% | P5 | G1 | §5.3 | All 8 NFR rows locked
D2 | P1 Discovery / G1 | D2-T4 | Stakeholder facts → artefact 03 | What to implement: Stakeholder facts → artefact 03 / Expected functionality: 15 roles + 5 conflicts; AI authority none/draft-only. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Roles/conflicts referenced; AI authority preserved | P2 | Critical | Not Started | 2026-08-06 | 2026-08-06 |  | D1-T4 |  | 0% | P4 | G1 | §6.3 | Roles/conflicts referenced; AI authority preserved
D2 | P1 Discovery / G1 | D2-T5 | Script stubs: setup/run/test/evaluate/reset + export capability | What to implement: Script stubs: setup/run/test/evaluate/reset + export capability / Expected functionality: Five name-matched scripts under submission/scripts/ plus evidence-export (export.* or documented export mode). Document invocation. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: 5 name-matched scripts + export capability documented | P3 | Critical | Not Started | 2026-08-06 | 2026-08-06 |  | D1-T2 |  | 0% | P5 | G1 | §7.2 G-26 | 5 name-matched scripts + export capability documented
D2 | P1 Discovery / G1 | D2-T6 | Review 03; Quality vs Mfg conflict note | What to implement: Review 03; Quality vs Mfg conflict note / Expected functionality: Independent review; own Quality vs Manufacturing conflict in writing. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Written review; no SoD breach | P4 | Critical | Not Started | 2026-08-06 | 2026-08-06 |  | D2-T1; D2-T4 |  | 0% | P1 (ack) | G1 | §6.3, §12 | Written review; no SoD breach
D2 | P1 Discovery / G1 | D2-T7 | Review 04; NFR sec/privacy rows | What to implement: Review 04; NFR sec/privacy rows / Expected functionality: Confirm prohibited uses + security/privacy NFR bars measurable. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Review confirms prohibited uses + NFR bars | P5 | Critical | Not Started | 2026-08-06 | 2026-08-06 |  | D2-T1; D2-T3 |  | 0% | P1 (ack) | G1 | §12, §5.3 | Review confirms prohibited uses + NFR bars
D3 | P2 Domain | D3-T1 | Draft 05 DDD + 06 Data gov | What to implement: Draft 05 DDD + 06 Data gov / Expected functionality: Bounded contexts A/B/C; ALCOA+; no silent normalize; 06 hard-gate aware. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Contexts + ALCOA+/hard-gate awareness | P2 | High | Not Started | 2026-08-07 | 2026-08-07 |  | G1 (D2) |  | 0% | P3 (05), P4 (06) |  | §8 P2, §12 | Contexts + ALCOA+/hard-gate awareness
D3 | P2 Domain | D3-T2 | Start 84-inject register mirror | What to implement: Start 84-inject register mirror / Expected functionality: Mirror under submission/evaluation/; challenge CSV untouched; rows start NOT_RUN. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Mirror path; progress countable | P2 | High | Not Started | 2026-08-07 | 2026-08-07 |  | D1-T4 |  | 0% | P4 |  | §11.1 | Mirror path; progress countable
D3 | P2 Domain | D3-T3 | RTM skeleton 09; RELATIONSHIP_MODEL checker design | What to implement: RTM skeleton 09; RELATIONSHIP_MODEL checker design / Expected functionality: Start artefact 09; fail-closed identity checker design. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Checker cites RELATIONSHIP_MODEL.csv; unique RTM IDs | P3 | High | Not Started | 2026-08-07 | 2026-08-07 |  | D3-T1 |  | 0% | P5 |  | §8 P2, §13 | Checker cites RELATIONSHIP_MODEL.csv; unique RTM IDs
D3 | P2 Domain | D3-T4 | Authority/provenance rules for 06; INJ-031 flag | What to implement: Authority/provenance rules for 06; INJ-031 flag / Expected functionality: Require status/authority/effective date; log validation ambiguity as conflict. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Rules + INJ-031 flagged | P4 | High | Not Started | 2026-08-07 | 2026-08-07 |  | D2 exit |  | 0% | P2 |  | §8 P2, §11 | Rules + INJ-031 flagged
D3 | P2 Domain | D3-T5 | Privacy/residency flags in register (D09) | What to implement: Privacy/residency flags in register (D09) / Expected functionality: Tag INJ-059–064; no silent minimization of GxP holds. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: INJ-059–064 tagged | P5 | High | Not Started | 2026-08-07 | 2026-08-07 |  | D2 exit |  | 0% | P4 |  | §11.1 D09 | INJ-059–064 tagged
D3 | P2 Domain | D3-T6 | Brownfield/TOM notes; global vs local conflict | What to implement: Brownfield/TOM notes; global vs local conflict / Expected functionality: Notes for artefact 26; conflict not prematurely resolved. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Notes exist; conflict open | P1 | High | Not Started | 2026-08-07 | 2026-08-07 |  | D2 exit |  | 0% | P4 |  | §6.3 | Notes exist; conflict open
D3 | P2 Domain | D3-T7 | Eval step 2: design eval-set coverage matrix | What to implement: Eval step 2: design eval-set coverage matrix / Expected functionality: Normal/edge/adversarial/metamorphic/outage; required/prohibited; hard-gate flags; expected_answer_included=no. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Matrix under datasets/; maps WF A/B/C | P5 (+P2) | High | Not Started | 2026-08-07 | 2026-08-07 |  | D1-T8; D3-T2 |  | 0% | P4 |  | §11.8 step 2 | Matrix under datasets/; maps WF A/B/C
D4 | P2 Domain / G2 | D4-T1 | Complete 07 + 08 (KG + simpler alternative) | What to implement: Complete 07 + 08 (KG + simpler alternative) / Expected functionality: Ontology/KG; 08 includes simpler-alternative benchmark; KG not mandatory without evidence (constraint 12). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Simpler-alternative benchmark; no forced KG | P2 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D3-T1 |  | 0% | P3 | G2 | §8 P2, §12, §20, constraint 12 | Simpler-alternative benchmark; no forced KG
D4 | P2 Domain / G2 | D4-T2 | Inject register: all 84 mapped or declared gap | What to implement: Inject register: all 84 mapped or declared gap / Expected functionality: Count=84; gaps in RAID/manifest; challenge CSV unmodified. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Count=84; no silent deletes | P2 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D3-T2; D3-T7 |  | 0% | P1 | G2 | §11.1 | Count=84; no silent deletes
D4 | P2 Domain / G2 | D4-T3 | RTM↔inject links; knowledge_catalog authority+hash stub | What to implement: RTM↔inject links; knowledge_catalog authority+hash stub / Expected functionality: Stub rejects superseded/untrusted when hash/status fail. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Stub demo recorded | P3 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D3-T3 |  | 0% | P5 | G2 | §13, §8 P2 | Stub demo recorded
D4 | P2 Domain / G2 | D4-T4 | Independent conflict review (ID/unit/time/authority/lineage) | What to implement: Independent conflict review (ID/unit/time/authority/lineage) / Expected functionality: List open conflicts; zero cleaned values as truth. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Written open-conflict list | P4 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D4-T2 |  | 0% | P1 | G2 | §8.2 G2 | Written open-conflict list
D4 | P2 Domain / G2 | D4-T5 | Spot-check sensitive injects INJ-041/059–064 | What to implement: Spot-check sensitive injects INJ-041/059–064 / Expected functionality: Deep-read privacy/access injects; log purpose/access limits. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Findings logged | P5 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D3 exit |  | 0% | P4 | G2 | §11.1 | Findings logged
D4 | P2 Domain / G2 | D4-T6 | Business challenge to unjustified KG | What to implement: Business challenge to unjustified KG / Expected functionality: Accept/reject KG scope with rationale. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Review note with rationale | P1 | Critical | Not Started | 2026-08-08 | 2026-08-08 |  | D3 exit |  | 0% | P2 | G2 | §20, §8.2 | Review note with rationale
D5 | P3 Architecture / G3 | D5-T1 | Artefacts 10 C4, 11 ADRs (≥10), 12 contracts | What to implement: Artefacts 10 C4, 11 ADRs (≥10), 12 contracts / Expected functionality: C4, ≥10 ADRs, contracts vs evaluation/contracts schemas; brownfield/rollback. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: ≥10 ADRs; schema reconciliation | P3 | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | G2 (D4) |  | 0% | P5 (10–12), P4 (GxP) | G3 | §8 P3, §12 | ≥10 ADRs; schema reconciliation
D5 | P3 Architecture / G3 | D5-T2 | Shared evidence-resolver (SHA-256 + source_preserved) | What to implement: Shared evidence-resolver (SHA-256 + source_preserved) / Expected functionality: Valid evidence_item; real 64-hex SHA-256; source_preserved=true. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Real hashes; source_preserved=true | P3 | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D5-T1 |  | 0% | P5 | G3 | §11.3, §13 | Real hashes; source_preserved=true
D5 | P3 Architecture / G3 | D5-T3 | python -B tools/test_contracts.py green | What to implement: python -B tools/test_contracts.py green / Expected functionality: 3 positive valid + 3 negative invalid. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: 3+/3− samples correct | P3 | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D5-T1; D5-T2 |  | 0% | P5 | G3 | §4.2, §13 | 3+/3− samples correct
D5 | P3 Architecture / G3 | D5-T4 | Draft 13–15 GxP/CSA/QRM | What to implement: Draft 13–15 GxP/CSA/QRM / Expected functionality: Intended use + GxP boundary; risk→control→test; RUB-09; every regulatory conclusion framed (constraint 13). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Boundary + RTM chains; jurisdiction/purpose/role on reg claims | P4 | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D4 exit |  | 0% | P5 | G3 | §8 P3, §12, constraint 13 | Boundary + RTM chains; jurisdiction/purpose/role on reg claims
D5 | P3 Architecture / G3 | D5-T5 | Threat skeleton; confirm negatives fail closed | What to implement: Threat skeleton; confirm negatives fail closed / Expected functionality: Disposition/reportability/side-effect samples still rejected. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Negatives still rejected | P5 | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D4 exit |  | 0% | P2 | G3 | §8 P3 | Negatives still rejected
D5 | P3 Architecture / G3 | D5-T6 | Domain rules for resolver; contract vs batch/PV facts | What to implement: Domain rules for resolver; contract vs batch/PV facts / Expected functionality: Map schema fields to sources; no silent unit/time conversion. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Written field→source mapping | P2 | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D4 exit |  | 0% | P3 | G3 | §13 | Written field→source mapping
D5 | P3 Architecture / G3 | D5-T7 | Ops fit review; ban adaptive undeclared transforms | What to implement: Ops fit review; ban adaptive undeclared transforms / Expected functionality: Biostats lens; finding in ADR or RAID. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Finding recorded | P1 | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D4 exit |  | 0% | P3 | G3 | §6.3 Biostats | Finding recorded
D5 | P3 Architecture / G3 | D5-T8 | Eval step 3: create offline eval tree | What to implement: Eval step 3: create offline eval tree / Expected functionality: datasets/adapters/graders/policies/reports + runner.py + README. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: All seven entries exist; runner stub callable | P5 (+P3) | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D3-T7; D5-T1 |  | 0% | P4 | G3 | §11.8 step 3, §7.2 | All seven entries exist; runner stub callable
D5 | P3 Architecture / G3 | D5-T9 | Policies stub: ten release gates + hard gates (score-independent) | What to implement: Policies stub: ten release gates + hard gates (score-independent) / Expected functionality: Automatic-fail rules for §11.5 gates + hard gates; hard gates apply independent of 180-pt score (constraint 14). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Each hard gate named; score-independence stated | P4 (+P5) | Critical | Not Started | 2026-08-09 | 2026-08-09 |  | D5-T8 |  | 0% | P5 | G3 | §11.5, constraint 14 | Each hard gate named; score-independence stated
D6 | P4 Secure design | D6-T1 | Draft 16 Threat + 17 Privacy | What to implement: Draft 16 Threat + 17 Privacy / Expected functionality: Injection/poisoning/tool abuse/stale auth/exfil/DoW; purpose limitation; RUB-10/11. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Threat+privacy cover hard gates | P5 | High | Not Started | 2026-08-10 | 2026-08-10 |  | G3 (D5) |  | 0% | P4 |  | §8 P4, §12 | Threat+privacy cover hard gates
D6 | P4 Secure design | D6-T2 | Write failing prohibited-action + stale-auth tests (INJ-065/066/067) | What to implement: Write failing prohibited-action + stale-auth tests (INJ-065/066/067) / Expected functionality: Tests-before-inference before WF implementation code. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Tests fail for right reason before WF code | P5 | High | Not Started | 2026-08-10 | 2026-08-10 |  | D6-T1; D1-T6 |  | 0% | P3 |  | §8 P4, constraint 4 | Tests fail for right reason before WF code
D6 | P4 Secure design | D6-T3 | Approved vs poisoned tool manifests; signed allowlist; agents OFF | What to implement: Approved vs poisoned tool manifests; signed allowlist; agents OFF / Expected functionality: Deny unsigned/poisoned; confirm agents still OFF pre-G4. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Deny design + agents OFF confirmed | P3 | High | Not Started | 2026-08-10 | 2026-08-10 |  | D5 exit |  | 0% | P5 |  | §13, agent freeze | Deny design + agents OFF confirmed
D6 | P4 Secure design | D6-T4 | Residual risk register start | What to implement: Residual risk register start / Expected functionality: List residual risks with owners; no unverified GxP acceptance. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Risks listed with owners | P4 | High | Not Started | 2026-08-10 | 2026-08-10 |  | D5 exit |  | 0% | P5 |  | §8 P4 | Risks listed with owners
D6 | P4 Secure design | D6-T5 | Privacy/purpose data mapping | What to implement: Privacy/purpose data mapping / Expected functionality: Map consents/exports/retention for D09. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Mapping cites conflicts | P2 | High | Not Started | 2026-08-10 | 2026-08-10 |  | D5 exit |  | 0% | P5 |  | §11.1 D09 | Mapping cites conflicts
D6 | P4 Secure design | D6-T6 | HF / automation-bias notes (INJ-071) for artefact 18 | What to implement: HF / automation-bias notes (INJ-071) for artefact 18 / Expected functionality: candidate_outputs / omitted-fact risk notes. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Notes cite INJ-071 | P1 | High | Not Started | 2026-08-10 | 2026-08-10 |  | D5 exit |  | 0% | P5 |  | §8 P4 | Notes cite INJ-071
D6 | P4 Secure design | D6-T7 | Eval step 5 start: ≥3 graders with ± unit tests | What to implement: Eval step 5 start: ≥3 graders with ± unit tests / Expected functionality: Schema/prohibited/evidence graders; + and − unit tests; thresholds draft until D7 freeze. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: ≥3 graders with ± tests | P5 | High | Not Started | 2026-08-10 | 2026-08-10 |  | D5-T8; D6-T2 |  | 0% | P3 |  | §11.8 step 5 | ≥3 graders with ± tests
D7 | P4 Secure design / G4 | D7-T1 | Draft 18 Responsible AI / human factors | What to implement: Draft 18 Responsible AI / human factors / Expected functionality: Automation-bias mitigations; a11y/language; reviewable outputs. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Mitigations + a11y risks | P1 | Critical | Not Started | 2026-08-11 | 2026-08-11 |  | D6-T6 |  | 0% | P5 | G4 | §8 P4 | Mitigations + a11y risks
D7 | P4 Secure design / G4 | D7-T2 | Draft 19–21 EU AI Act / ISO-aligned / assurance | What to implement: Draft 19–21 EU AI Act / ISO-aligned / assurance / Expected functionality: Jurisdiction/purpose/role/boundary/risk class on every reg conclusion; no certification claim. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Framing complete; no cert claim | P4 | Critical | Not Started | 2026-08-11 | 2026-08-11 |  | D6 exit |  | 0% | P5 (19–20), P1 (21) | G4 | §8 P4, constraint 13 | Framing complete; no cert claim
D7 | P4 Secure design / G4 | D7-T3 | Cursor engineering evidence in ADRs (Must) | What to implement: Cursor engineering evidence in ADRs (Must) / Expected functionality: ≥1 ADR cites rules/skills/commands including engineering-principles.mdc; plan reviewer outputs under submission/evidence/. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: ADR citation + evidence path planned | P3 | Critical | Not Started | 2026-08-11 | 2026-08-11 |  | D6 exit |  | 0% | P1 | G4 | §15 Must, G-33 | ADR citation + evidence path planned
D7 | P4 Secure design / G4 | D7-T4 | Control↔test map; every hard-gate threat has failing test | What to implement: Control↔test map; every hard-gate threat has failing test / Expected functionality: threat→test→expected fail; required for G4. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Traceability table complete | P5 | Critical | Not Started | 2026-08-11 | 2026-08-11 |  | D6-T2; D6-T1 |  | 0% | P3 | G4 | §8.2 G4 | Traceability table complete
D7 | P4 Secure design / G4 | D7-T5 | Cross-check assurance claims vs evidence register | What to implement: Cross-check assurance claims vs evidence register / Expected functionality: No claim without register evidence path. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Unsupported claims removed/downgraded | P2 | Critical | Not Started | 2026-08-11 | 2026-08-11 |  | D6 exit |  | 0% | P4 | G4 | §11 | Unsupported claims removed/downgraded
D7 | P4 Secure design / G4 | D7-T6 | Freeze grader/suite thresholds before improved results | What to implement: Freeze grader/suite thresholds before improved results / Expected functionality: Commit thresholds in decision log; no post-hoc softening without RAID (R-007). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents OFF until G4 PASS; ratify Plan V2 as SoT; author ≠ sole approver. / Expected output / completion criteria: Threshold commit logged | P5 | Critical | Not Started | 2026-08-11 | 2026-08-11 |  | D6-T7; D5-T9 |  | 0% | P4 | G4 | §11.8, R-007 | Threshold commit logged
D8 | P5 POC build | D8-T1 | Shared resolver + Workflow A + app shell | What to implement: Shared resolver + Workflow A + app shell / Expected functionality: WF-A advisory; readiness_state only; no disposition; app text nodes — no innerHTML. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Schema-valid; no disposition; no innerHTML | P3 | High | Not Started | 2026-08-12 | 2026-08-12 |  | G4 (D7); D5-T2; D6-T2 |  | 0% | P5 (+P4 GxP) |  | §13, RUB-08 | Schema-valid; no disposition; no innerHTML
D8 | P5 POC build | D8-T2 | Start Workflow C (draft options) | What to implement: Start Workflow C (draft options) / Expected functionality: All options draft; no_side_effects=true on success/error. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: draft + no_side_effects=true | P3 | High | Not Started | 2026-08-12 | 2026-08-12 |  | D8-T1 |  | 0% | P5 |  | §13 | draft + no_side_effects=true
D8 | P5 POC build | D8-T3 | WF-A domain rules + sign-off criteria | What to implement: WF-A domain rules + sign-off criteria / Expected functionality: Forbid release/reject/recall language in outputs. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Sign-off checklist forbids disposition language | P4 | High | Not Started | 2026-08-12 | 2026-08-12 |  | D7 exit |  | 0% | P3 |  | §6.4, §13 | Sign-off checklist forbids disposition language
D8 | P5 POC build | D8-T4 | WF-C domain rules (ethics, approvals_required) | What to implement: WF-C domain rules (ethics, approvals_required) / Expected functionality: No reserve/allocate/ship verbs; named approvals. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: No side-effect verbs; approvals named | P1 | High | Not Started | 2026-08-12 | 2026-08-12 |  | D7 exit |  | 0% | P4 |  | §6.4, §13 | No side-effect verbs; approvals named
D8 | P5 POC build | D8-T5 | PV domain rules prep for B; verbatim preservation | What to implement: PV domain rules prep for B; verbatim preservation / Expected functionality: source_facts/clocks/listedness/required_reviews; no final safety conclusions. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Verbatim preservation rules written | P2 | High | Not Started | 2026-08-12 | 2026-08-12 |  | D7 exit |  | 0% | P4 |  | §13 | Verbatim preservation rules written
D8 | P5 POC build | D8-T6 | Tests for A + authz-at-execution; execution_status=not_executed | What to implement: Tests for A + authz-at-execution; execution_status=not_executed / Expected functionality: Allow path; deny revoked/stale (INJ-067); contracts still 3+/3−. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Allow/deny paths evidenced | P5 | High | Not Started | 2026-08-12 | 2026-08-12 |  | D7 exit |  | 0% | P4 |  | §13, INJ-067 | Allow/deny paths evidenced
D8 | P5 POC build | D8-T7 | Eval step 4: build adapter | What to implement: Eval step 4: build adapter / Expected functionality: Adapter captures trajectory metrics; wire WF-A; C/B stubs OK. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Adapter under adapters/; no silent side effects | P3 | High | Not Started | 2026-08-12 | 2026-08-12 |  | D5-T8; D8-T1 |  | 0% | P5 |  | §11.8 step 4 | Adapter under adapters/; no silent side effects
D8 | P5 POC build | D8-T8 | Eval step 6 baseline on unmodified starter/ | What to implement: Eval step 6 baseline on unmodified starter/ / Expected functionality: reports/baseline/summary.json + failed_cases.json (or documented gaps). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Baseline report set present | P5 | High | Not Started | 2026-08-12 | 2026-08-12 |  | D8-T7; D6-T7 |  | 0% | P3 |  | §11.8 step 6, M6b | Baseline report set present
D9 | P5 POC build / G5 | D9-T1 | Finish WF-C then WF-B; AI-disabled path + scripts | What to implement: Finish WF-C then WF-B; AI-disabled path + scripts / Expected functionality: Build order A→C→B. AI-disabled schema-valid. Document scripts including export. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Order respected; AI-off valid; scripts+export documented | P3 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D8-T1; D8-T2 |  | 0% | P5 | G5 | §13, §8 P5 | Order respected; AI-off valid; scripts+export documented
D9 | P5 POC build / G5 | D9-T2 | Finalize WF-C options + demo narrative | What to implement: Finalize WF-C options + demo narrative / Expected functionality: Demo shows draft-only + constraint violations. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Demo script draft-only | P1 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D8 exit |  | 0% | P4 | G5 | §6.4 | Demo script draft-only
D9 | P5 POC build / G5 | D9-T3 | Finalize WF-B domain (duplicates/clocks/listedness/reviews) | What to implement: Finalize WF-B domain (duplicates/clocks/listedness/reviews) / Expected functionality: Required PV fields; no final safety conclusions. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: PV fields populated; no final safety | P2 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D8 exit |  | 0% | P4 | G5 | §11.3 PV | PV fields populated; no final safety
D9 | P5 POC build / G5 | D9-T4 | Dual PV sign-off P2+P4; continuity PV max_ai_outage_hours=0 | What to implement: Dual PV sign-off P2+P4; continuity PV max_ai_outage_hours=0 / Expected functionality: Joint sign; schema scan no prohibited properties; document PV AI-outage window = 0h with manual runbook required (constraint 5). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Joint sign + PV 0h continuity stated | P4 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D9-T3 |  | 0% | P5 | G5 | §6.4, constraint 5, continuity CSV | Joint sign + PV 0h continuity stated
D9 | P5 POC build / G5 | D9-T5 | Prohibited-action suite fail-closed; subgroup smoke; kill switch | What to implement: Prohibited-action suite fail-closed; subgroup smoke; kill switch / Expected functionality: Negatives fail; ≥1 abstain; kill switch / safe degradation demonstrated for Track A Must. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Fail-closed + kill switch evidence | P5 | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D6-T2; D9-T1 |  | 0% | P3 | G5 | §11.5, constraint 5 | Fail-closed + kill switch evidence
D9 | P5 POC build / G5 | D9-T6 | MVP demo pack (happy + abstain) | What to implement: MVP demo pack (happy + abstain) / Expected functionality: Recorded run with scenario IDs, hashes, reviewer, gate outcome. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Recorded happy + abstain | All | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D9-T1; D9-T2; D9-T3 |  | 0% | P1 facilitates | G5 | §8.2 G5, M5 | Recorded happy + abstain
D9 | P5 POC build / G5 | D9-T7 | AI-disabled continuity: batch/supply 14d; PV 0h | What to implement: AI-disabled continuity: batch/supply 14d; PV 0h / Expected functionality: Runbook paths prove batch & supply 14-day AI-disabled; PV has no multi-day AI-disabled claim — manual path only. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Continuity matrix matches continuity_requirements.csv | P5 (+P1) | Critical | Not Started | 2026-08-13 | 2026-08-13 |  | D9-T1 |  | 0% | P4 | G5 | constraint 5, INJ-082 | Continuity matrix matches continuity_requirements.csv
D10 | P6–P8 TEVV / Ops / Defence | D10-T1 | Artefacts 22–25; 12 suites via eval stack; red-team/outage | What to implement: Artefacts 22–25; 12 suites via eval stack; red-team/outage / Expected functionality: Full runner+graders+policies; pre-committed thresholds; ≥1 failed-gate demo; hard gates score-independent. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: 12 suites evidenced; failed-gate demo | P5 | Critical | Not Started | 2026-08-14 | 2026-08-14 |  | G5 (D9); D7-T6 |  | 0% | P4 (22,24,25), P3 (outage) | G6 | §8 P6, §11.4–11.5, §11.8 | 12 suites evidenced; failed-gate demo
D10 | P6–P8 TEVV / Ops / Defence | D10-T2 | Write test_results.json + evaluation_results.json (§7.3 schemas) | What to implement: Write test_results.json + evaluation_results.json (§7.3 schemas) / Expected functionality: Fields: suite,test_id,requirement/control IDs,result,timestamp,runtime_mode,evidence_path; and dataset/cohort,grader,threshold,observed,gate_result,evidence_path. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Required fields present; JSON parses | P5 | Critical | Not Started | 2026-08-14 | 2026-08-14 |  | D10-T1 |  | 0% | P3 | G6 | §7.3, SUBMISSION_EVIDENCE_STANDARD | Required fields present; JSON parses
D10 | P6–P8 TEVV / Ops / Defence | D10-T3 | Artefacts 23/26/29/30; fold delivery FinOps into 23 | What to implement: Artefacts 23/26/29/30; fold delivery FinOps into 23 / Expected functionality: Cite finops_delivery_log.csv; human review cost; recommendation enum draft. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: FinOps log cited; pitch residual risk | P1 | High | Not Started | 2026-08-14 | 2026-08-14 |  | D9 exit |  | 0% | P5 (23), P4 (26/29/30) | G6–G8 | §8 P6–P8, §11.9, §12 | FinOps log cited; pitch residual risk
D10 | P6–P8 TEVV / Ops / Defence | D10-T4 | Subgroup/multilingual evidence; inspection support; PV suites | What to implement: Subgroup/multilingual evidence; inspection support; PV suites / Expected functionality: Subgroup gaps explicit; inspection path to immutable evidence. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Subgroup gaps explicit | P2 | Critical | Not Started | 2026-08-14 | 2026-08-14 |  | D9 exit |  | 0% | P5 | G6 | §11.4 #7/#10 | Subgroup gaps explicit
D10 | P6–P8 TEVV / Ops / Defence | D10-T5 | Clean-room including export; freeze; hash; --final | What to implement: Clean-room including export; freeze; hash; --final / Expected functionality: Clean-room §18 with setup/run/test/evaluate/reset/export; hash --check; --final PASS; no secrets. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Preflight×2; export demonstrated; --check/--final PASS | P3 | Critical | Not Started | 2026-08-14 | 2026-08-14 |  | D10-T1; D10-T2 |  | 0% | Outsider + P5 | G7 | §4.3, §18, §19, G-26 | Preflight×2; export demonstrated; --check/--final PASS
D10 | P6–P8 TEVV / Ops / Defence | D10-T6 | Inspection drill; residual risk; defence 4/5/11; artefact 27 | What to implement: Inspection drill; residual risk; defence 4/5/11; artefact 27 / Expected functionality: Inspection drill; residual risk; vendor exit 27 for RUB-15. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Drill record; 27 addressed | P4 | High | Not Started | 2026-08-14 | 2026-08-14 |  | D9 exit |  | 0% | P5 | G7–G8 | §11.6, §12 | Drill record; 27 addressed
D10 | P6–P8 TEVV / Ops / Defence | D10-T7 | Rehearse 13 defence elements; board recommendation | What to implement: Rehearse 13 defence elements; board recommendation / Expected functionality: Named presenter per element; go/conditional/pivot/pause/stop recorded. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Presenters + recommendation | All | Critical | Not Started | 2026-08-14 | 2026-08-14 |  | D9 exit |  | 0% | Full team | G8 | §11.6, §8.2 G8 | Presenters + recommendation
D10 | P6–P8 TEVV / Ops / Defence | D10-T8 | Eval reports + human rubric + regression history (+ judge controls if used) | What to implement: Eval reports + human rubric + regression history (+ judge controls if used) / Expected functionality: Emit full report set; calibrated human rubric; regression history; LLM-judge controls if LLM judge used (§11.4 Must). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Report set + rubric + regression history present | P5 | Critical | Not Started | 2026-08-14 | 2026-08-14 |  | D8-T8; D10-T1 |  | 0% | P2 | G6 | §11.4, §11.8, G-28 | Report set + rubric + regression history present
D10 | P6–P8 TEVV / Ops / Defence | D10-T9 | Close FinOps delivery log through D10; efficiency summary | What to implement: Close FinOps delivery log through D10; efficiency summary / Expected functionality: All Track-A days have rows; summary for artefact 23 / defence element 9. Do not weaken validation to cut cost. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: All Track-A days logged; summary written | P1 | High | Not Started | 2026-08-14 | 2026-08-14 |  | D1-T9; D10-T3 |  | 0% | P5 | G6–G8 | §11.9 | All Track-A days logged; summary written
D10 | P6–P8 TEVV / Ops / Defence | D10-T10 | Four submission runbooks complete (SETUP/OPERATIONS/INCIDENT/AI_DISABLED) | What to implement: Four submission runbooks complete (SETUP/OPERATIONS/INCIDENT/AI_DISABLED) / Expected functionality: Each command: prerequisites, inputs, expected outputs, failure handling, reset/rollback. Package PARTICIPANT/REPO guides are not substitutes (G-37). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Four named runbooks with required sections | P5 (+P1) | Critical | Not Started | 2026-08-14 | 2026-08-14 |  | D9-T1; D9-T7 |  | 0% | P3 | G7 | §7.2, §7.3, G-37 | Four named runbooks with required sections
D11 | P9 Hardening | D11-T1 | App packaging & config; versioned RC; locked deps | What to implement: App packaging & config; versioned RC; locked deps / Expected functionality: RC version ID + lockfile/stdlib mode documented. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: RC version + lock/stdlib documented | P3 | High | Not Started | 2026-08-15 | 2026-08-15 |  | G8 (D10) |  | 0% | P5 | P9 | §8.1 | RC version + lock/stdlib documented
D11 | P9 Hardening | D11-T2 | Observability & SLOs / error budget | What to implement: Observability & SLOs / error budget / Expected functionality: SLIs/SLOs/metrics/logs vs G1 NFRs; error budget. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Metrics/logs + error budget stated | P5+P3 | High | Not Started | 2026-08-15 | 2026-08-15 |  | D10 exit |  | 0% | P4 | P9 | §8.1, D11 SLO | Metrics/logs + error budget stated
D11 | P9 Hardening | D11-T3 | Support runbooks polish (OPS, INCIDENT, AI-disabled, kill switch) | What to implement: Support runbooks polish (OPS, INCIDENT, AI-disabled, kill switch) / Expected functionality: Complete/verify OPERATIONS, INCIDENT, AI_DISABLED + kill switch; SETUP already from D10-T10. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Prereq/IO/failure/rollback sections present | P1+P5 | High | Not Started | 2026-08-15 | 2026-08-15 |  | D10-T10 |  | 0% | P3 | P9 | §8.1, §7.2 | Prereq/IO/failure/rollback sections present
D11 | P9 Hardening | D11-T4 | Accessibility smoke; readiness gaps for 28 | What to implement: Accessibility smoke; readiness gaps for 28 / Expected functionality: Keyboard critical-path; gaps into artefact 28 backlog. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Keyboard result logged | P4+P1 | High | Not Started | 2026-08-15 | 2026-08-15 |  | D10 exit |  | 0% | P5 | P9 | §8.1 | Keyboard result logged
D11 | P9 Hardening | D11-T5 | Domain regression checklist on RC | What to implement: Domain regression checklist on RC / Expected functionality: A/B/C boundary regressions checklist for RC sign-off. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Checklist covers A/B/C | P2 | High | Not Started | 2026-08-15 | 2026-08-15 |  | D10 exit |  | 0% | P4 | P9 | §8.1 / owes | Checklist covers A/B/C
D12 | P9 Hardening | D12-T1 | Security retest on RC | What to implement: Security retest on RC / Expected functionality: Re-execute critical threat controls on RC; PASS/FAIL logged. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: RC retest logged | P5 | High | Not Started | 2026-08-16 | 2026-08-16 |  | D11-T1 |  | 0% | P4 | P9 | §8.1 | RC retest logged
D12 | P9 Hardening | D12-T2 | Backup/restore + rollback; RTO/RPO evidence | What to implement: Backup/restore + rollback; RTO/RPO evidence / Expected functionality: Restore drill evidence; RTO/RPO vs NFRs. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Restore path + RTO/RPO numbers | P3+P5 | High | Not Started | 2026-08-16 | 2026-08-16 |  | D11 exit |  | 0% | P4 | P9 | §8.1 | Restore path + RTO/RPO numbers
D12 | P9 Hardening | D12-T3 | Performance/budget soak | What to implement: Performance/budget soak / Expected functionality: Within declared budgets or CONDITIONAL with RAID. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Within budgets or RAID CONDITIONAL | P5 | High | Not Started | 2026-08-16 | 2026-08-16 |  | D11 exit |  | 0% | P1 | P9 | §8.1 | Within budgets or RAID CONDITIONAL
D12 | P9 Hardening | D12-T4 | TOM support tiers; release decision prep | What to implement: TOM support tiers; release decision prep / Expected functionality: L1/L2/L3 named; release decision template for G9. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Support tiers + template ready | P1 | High | Not Started | 2026-08-16 | 2026-08-16 |  | D11 exit |  | 0% | P4 | P9 | §8.1 | Support tiers + template ready
D12 | P9 Hardening | D12-T5 | RC domain regression sign-off | What to implement: RC domain regression sign-off / Expected functionality: Sign no A/B/C boundary regression on RC. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Sign record | P2 | High | Not Started | 2026-08-16 | 2026-08-16 |  | D11 exit |  | 0% | P4 | P9 | owes G9 | Sign record
D12 | P9 Hardening | D12-T6 | Residual risk update for board | What to implement: Residual risk update for board / Expected functionality: Refresh residual risk for Readiness Board. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Risk list current | P4 | High | Not Started | 2026-08-16 | 2026-08-16 |  | D11 exit |  | 0% | P5 | P9 | §8.1 G9 | Risk list current
D12 | P9 Hardening | D12-T7 | P9 validation checklist (AEGIS-adapted readiness) | What to implement: P9 validation checklist (AEGIS-adapted readiness) / Expected functionality: Offline; scripts+export; contracts/prohibited; eval gates; no secrets; no fabricated completion claims; a11y; soak; license/vuln note; hard gates on RC. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Checklist completed with evidence paths | P5 (+P3) | Critical | Not Started | 2026-08-16 | 2026-08-16 |  | D12-T1; D12-T3 |  | 0% | P4 | P9 | §8.1 P9 checklist | Checklist completed with evidence paths
D13 | P9 Readiness / G9 | D13-T1 | Chair Production Readiness Board (artefact 28) | What to implement: Chair Production Readiness Board (artefact 28) / Expected functionality: Blockers=0 or No-Go; minutes; no prod-ready language without PASS. Fresh context for board (§15.1). / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Blockers=0 or No-Go; minutes | P4 | Critical | Not Started | 2026-08-17 | 2026-08-17 |  | D12-T6; D12-T1; D12-T7 |  | 0% | Board (all) | G9 | §8.1, §8.2 G9, §15.1 | Blockers=0 or No-Go; minutes
D13 | P9 Readiness / G9 | D13-T2 | RC tag + manifest; clean-room on RC (incl. export) | What to implement: RC tag + manifest; clean-room on RC (incl. export) / Expected functionality: Immutable RC tag; repeat clean-room with export on RC extract. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Tag immutable; RC clean-room PASS | P3 | Critical | Not Started | 2026-08-17 | 2026-08-17 |  | D11-T1; D10-T5 |  | 0% | Outsider + P5 | G9 | §8.1, §18 | Tag immutable; RC clean-room PASS
D13 | P9 Readiness / G9 | D13-T3 | Release decision sign; G9 minutes | What to implement: Release decision sign; G9 minutes / Expected functionality: Signed go/no-go; if No-Go, strip production-ready language. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Signed go/no-go | P1 | Critical | Not Started | 2026-08-17 | 2026-08-17 |  | D12 exit |  | 0% | P4 | G9 | §8.1, constraint 8 | Signed go/no-go
D13 | P9 Readiness / G9 | D13-T4 | Security sign at G9 | What to implement: Security sign at G9 / Expected functionality: Written sec sign referencing RC retest. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Written sec sign | P5 | Critical | Not Started | 2026-08-17 | 2026-08-17 |  | D12 exit |  | 0% | P4 | G9 | §8.1 | Written sec sign
D13 | P9 Readiness / G9 | D13-T5 | Domain sign at board | What to implement: Domain sign at board / Expected functionality: Written domain sign: boundary obligations hold on RC. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Written domain sign | P2 | Critical | Not Started | 2026-08-17 | 2026-08-17 |  | D12 exit |  | 0% | P4 | G9 | owes G9 | Written domain sign
D14 | Buffer | D14-T1 | Buffer / defect burn-down | What to implement: Buffer / defect burn-down / Expected functionality: Close defects or defer with RAID; keep defence pack stable. / Important considerations: Work only under submission/; preserve immutable challenge evidence; Agents only after G4 PASS; no prohibited autonomy; Plan V2 SoT. / Expected output / completion criteria: Defects closed or RAID-deferred | All | Medium | Not Started | 2026-08-18 | 2026-08-18 |  | D13 exit |  | 0% | Stream backups | Buffer | §5.4 | Defects closed or RAID-deferred

## By_Day
Day | Task count | Not Started | In Progress | Blocked | Completed | On Hold | Avg completion
D1 | 11
D2 | 7
D3 | 7
D4 | 6
D5 | 9
D6 | 7
D7 | 6
D8 | 8
D9 | 7
D10 | 10
D11 | 5
D12 | 7
D13 | 5
D14 | 1

## Gate_Board
Gate | Day | Evaluation question | Reviewers | Pass criteria | Gate result | Notes
Preflight | D1 | Package integrity baseline + team ready? | Full team | Hour-0 PASS archived; seats named; Plan V2 ratified; --scaffold PASS; Cursor roots confirmed
G1 | D2 | Problem measurable; no-AI honest; NFRs locked? | P4 + P5 | 01–04 drafted with citations; no-AI table; NFR table locked; stop/pivot stated
G2 | D4 | Conflicts tracked not silently resolved; inject register real? | P1 + P4 | Conflict list exists; register 84 rows; no cleaned units/IDs; KG not forced
G3 | D5 | Prohibited actions outside executable boundary? | P2 + P5 | test_contracts 3+/3−; design forbids disposition/reportability/side effects
G4 | D7 | Threat/privacy/ISO controls + failing prohibited tests exist? | P1 + P3 | 16–21 drafted; prohibited/stale-auth tests fail for right reason before WF code; thresholds frozen
G5 | D9 | Three workflows run offline against fixtures? | P1 + P4 | A/B/C offline; schema-valid; demo happy+abstain; AI-disabled; continuity batch/supply 14d, PV 0h
G6 | D10 | Red-team / outage / cost gates fail closed as designed? | P2 + P3 | Suites evidence; failed-gate demo; thresholds pre-committed; human rubric + regression history
G7 | D10 | Clean-room + export + --final + hash --check? | Full team + outsider | Clean extract succeeds; export demonstrated; hashes match; --final PASS; four runbooks present
G8 | D10 | 13 defence elements rehearsed; recommendation clear? | Full team | Presenters named; go/conditional/pivot/pause/stop recorded
G9 | D13 | Readiness Board; Blockers=0; RC clean-room? | P4 chairs | 28 complete; hard gates on RC (score-independent); RC clean-room+export; P1/P4/P5 signs; no prod-ready language without PASS

## Gap_Log_V1_to_V2
Gap | V1 tracker issue | V2 correction
G-T1 | Instructions cite daywise v1.4 + FINAL; regenerate path under submission/ | SoT = Plan V2 + daywise MD; regenerate via ProjectPlan/_build_daywise_tracker_v2.py
G-T2 | D1-T7 ratify FINAL | D1-T7 ratify AEGIS_PROJECT_PLAN_V2.md
G-T3 | Assigned To used FDE-* only | P1–P5 primary labels (≡ FDE-1…5)
G-T4 | Scripts task omitted evidence-export | D2-T5 + D10-T5 require export capability
G-T5 | AI-disabled flattened to 14-day for all WF | D9-T4/D9-T7 enforce batch/supply 14d; PV 0h
G-T6 | Eval human rubric / regression / judge controls missing | D10-T8 added
G-T7 | FinOps CSV schema drifted from Plan V2 §11.9 | D1-T9 uses V2 header
G-T8 | Four submission runbooks incomplete in tracker | D10-T10 + D11-T3 cover SETUP/OPS/INCIDENT/AI_DISABLED
G-T9 | Cursor operating method / engineering-principles absent | D1-T10 + D7-T3 Must evidence
G-T10 | Hard gates vs 180-pt score not on Gate_Board | G3/G6/G9 pass criteria updated
G-T11 | P9 readiness checklist incomplete | D12-T7 + G9 criteria include no secrets / no fabricated claims / export
G-T12 | ProjectPlan mirror to submission not tasked | D1-T11 added
G-T13 | Kill switch only implicit on Track B | D9-T5 Track A kill switch/safe degradation