## Instructions
AEGIS Project Swimlane Tracker V2
Source: AEGIS_PROJECT_SWIMLANE_V2.md + AEGIS_PROJECT_PLAN_V2.md
Classification: Synthetic training only — not for real GxP / PV / supply / recall decisions.
Seat labels: FDE1–FDE5 (plan people seats; formerly P1–P5). Phase IDs remain P0–P9.
Sheets
Phase_Matrix — phases as rows; Author/Must-review from Gate_RACI; seats FDE1–FDE5 as columns
Day_Matrix — days as rows; Author/Must-review from Gate_RACI; seats FDE1–FDE5 as columns
RACI SoT: Gate_RACI = Plan V2 §8.2. Phase/Day focus text must not invent different must-reviewers.
Phase_Tasks — flat tracker: one row per seat × phase (50 = 10×5)
Day_Tasks — flat tracker: one row per seat × day (70 = 14×5)
Gate_RACI — gate author / reviewers mapped to phase + day
Workflow_RACI — Workflow A/B/C + shared resolver ownership
Owes — G8 defence owes and G9 extras by seat
Rules from plan
Agents / model-inference OFF until G4 PASS; deterministic core always on.
POC build order (phase P5): evidence-resolver → Workflow A → C → B.
Track A = D1–D10 / P0–P8 / G1–G8 (40h). Track B = D11–D14 / P9 / G9 (optional).
Never claim production-ready without G9.
Writable boundary: submission/ only. Challenge evidence immutable.
Regenerate + validate
python -B submission/artefacts/ProjectPlan/_build_swimlane_tracker_v2.py
python -B submission/artefacts/ProjectPlan/_build_swimlane_tracker_v2.py --validate-only

## Phase_Matrix
Phase | Phase Name | Hours | Exit Gate | Author / Chair | Must Review | Track | Option B+ Days | FDE1 · Value (V) Product / Value Lead | FDE2 · Domain (D) Domain / Evidence Lead | FDE3 · Architecture (A) Architecture / Build Lead | FDE4 · GxP / Quality (Q) GxP / Quality / ISO / Assurance Lead | FDE5 · Security / Eval (S) Security / Privacy / Eval / Reliability Lead
P0 | Preflight | 0–2 | Preflight | All | — | A | D1 | Charter / plan ratification | Case + inject skim | Scaffold + Hour-0 archive | Constraints catalogue | Constraints catalogue
P1 | Discovery | 2–7 | G1 | FDE1 | FDE4 + FDE5 | A | D1, D2 | Author G1 — artefacts 01–04 + production NFRs | Inject skim support | Scripts skeleton | Must-review G1 — constraints catalogue | Must-review G1 — NFR / threat notes
P2 | Domain | 7–12 | G2 | FDE2 | FDE1 + FDE4 | A | D3, D4 | Must-review G2 | Author G2 — artefacts 05–08 + 84-inject register | RTM / RELATIONSHIP_MODEL start | Must-review G2 — authority / lineage | Privacy / eval support (not G2 must-review)
P3 | Architecture | 12–18 | G3 | FDE3 + FDE4 | FDE2 + FDE5 | A | D5 | Architecture support (not G3 must-review) | Must-review G3 — RTM 09 + language | Author G3 — artefacts 10–12 + evidence-resolver | Co-author G3 — artefacts 13–15 GxP/CSA/QRM | Must-review G3 — threat skeleton + contract tests
P4 | Secure design | 18–23 | G4 | FDE5 + FDE4 | FDE1 + FDE3 | A | D6, D7 | Must-review G4 — artefact 18 RAI | Domain support (not G4 must-review) | Must-review G4 — Cursor evidence; build prep | Co-author G4 — artefacts 19–21 ISO / EU AI Act | Author G4 — artefacts 16–17 + failing prohibited tests
P5 | POC build | 23–31 | G5 | FDE3 + domain | FDE1 + FDE4 | A | D8, D9 | Must-review G5 — Workflow C domain + UX | Workflow B domain rules | Author G5 — build A→C→B + app + scripts | Must-review G5 — Workflow A readiness rules | Golden / edge / adversarial tests
P6 | TEVV | 31–35 | G6 | FDE5 | FDE2 + FDE3 | A | D10 | FinOps 23 + delivery FinOps | Must-review G6 — clinical / PV inject suites | Must-review G6 — adapter wire + outage path | Reg-authority suites | Author G6 — runner / graders / policies / reports
P7 | Ops + clean-room | 35–38 | G7 | FDE3 + FDE5 | Full team + outsider | A | D10 | 26 TOM + 29 runway (G7 full-team review) | Domain freeze sign (G7 full-team review) | Author G7 — evidence files + clean-room | 27/28 draft (G7 full-team review) | Co-author G7 — runbooks + eval evidence
P8 | Defence | 38–40 | G8 | FDE1 leads | Full team | A | D10 | Author G8 — pitch 30 + ship decision | Defence domain demos (G8 full-team review) | Freeze + hash (G8 full-team review) | GxP defence proof (G8 full-team review) | Red-team / outage demos (G8 full-team review)
P9 | Production hardening | +16–24 | G9 | FDE4 chairs | FDE3 tech · FDE5 sec · FDE1 release | B | D11, D12, D13, D14 | G9 release decision / L1 runbook | RC domain regression | G9 tech — RC packaging / rollback / tag | Author G9 — chair Readiness Board 28 | G9 security sign — SLO / sec retest

## Day_Matrix
Day | Day Focus | Gate | Author / Chair | Must Review | Phase(s) | Track | FDE1 · Value (V) Product / Value Lead | FDE2 · Domain (D) Domain / Evidence Lead | FDE3 · Architecture (A) Architecture / Build Lead | FDE4 · GxP / Quality (Q) GxP / Quality / ISO / Assurance Lead | FDE5 · Security / Eval (S) Security / Privacy / Eval / Reliability Lead
D1 | Preflight + SCQA start | Preflight | All | — | P0/P1 | A | SCQA start | Case read | Scaffold + Hour-0 baseline archive | Constraints catalogue start | Constraints / NFR notes start
D2 | Business case, stakeholders, blueprint, prod NFRs | G1 | FDE1 | FDE4 + FDE5 | P1 | A | Author G1 — business case / NFRs / artefacts 01–04 | Inject skim support | Scripts skeleton | Must-review G1 (with FDE5) | Must-review G1 — NFR lock (with FDE4)
D3 | DDD + data gov + brownfield | — | — | — | P2 | A | Stakeholder / value support | DDD + data gov (05–06) | Brownfield map / RTM start | Authority notes | Eval dataset design start
D4 | Ontology + KG + inject map | G2 | FDE2 | FDE1 + FDE4 | P2 | A | Must-review G2 (with FDE4) | Author G2 — ontology / KG / inject map | RELATIONSHIP_MODEL checker start | Must-review G2 — authority / lineage | Privacy / eval support (not G2 must-review)
D5 | C4 + ADR + contracts + GxP | G3 | FDE3 + FDE4 | FDE2 + FDE5 | P3 | A | Architecture support (not G3 must-review) | Must-review G3 — RTM 09 + language | Author G3 — C4 / ADR / contracts / resolver | Co-author G3 — GxP artefacts 13–15 | Must-review G3 — threat skeleton + contract tests
D6 | Threat modelling + privacy + security tests | — | — | — | P4 | A | RAI 18 draft (prep for G4 must-review) | Domain support for threat model (not G4 must-review) | Build prep / Cursor evidence (prep for G4 must-review) | Privacy / QRM support (prep for G4 co-author) | Threat modelling + privacy + security tests
D7 | ISO 42001 + EU AI Act + assurance + human factors | G4 | FDE5 + FDE4 | FDE1 + FDE3 | P4 | A | Must-review G4 (with FDE3) | Domain support (not G4 must-review) | Must-review G4 (with FDE1) | Co-author G4 — ISO / EU AI Act / assurance | Author G4 — failing prohibited tests
D8 | Build WF A (+ resolver) + app shell; start C | — | — | — | P5 | A | Supply path start (WF C domain) | WF B domain prep | WF A + evidence-resolver + app shell; start C | WF A readiness rules | Tests for WF A / prohibited paths
D9 | Finish C + B; AI-disabled; MVP demo | G5 | FDE3 + domain | FDE1 + FDE4 | P5 | A | Must-review G5 — WF C + MVP demo | WF B domain rules | Author G5 — finish C + B; AI-disabled scripts | Must-review G5 — WF A rules finalize | AI-disabled tests + MVP test evidence
D10 | TEVV / FinOps / clean-room / defence | G6–G8 | G6:FDE5 · G7:FDE3+FDE5 · G8:FDE1 | G6:FDE2+FDE3 · G7/G8:Full team | P6/P7/P8 | A | Author G8 — FinOps + defence pitch (also G7 full-team) | Must-review G6 — inject suites (clinical/PV); G7/G8 full-team | Must-review G6; Author G7 — clean-room / freeze; G8 full-team | Assurance + GxP defence proof (G7/G8 full-team) | Author G6 — TEVV reports; Co-author G7; G8 full-team
D11 | P9: SLO, runbooks, packaging | — | — | — | P9 | B | Support runbooks (L1) | RC domain regression prep | App packaging & config | Accessibility smoke prep | Observability & SLOs
D12 | P9: security retest, backup/restore, rollback | — | — | — | P9 | B | Release decision draft | Domain regression execute | Backup/restore + rollback evidence | Residual risk draft | Security retest + backup/restore
D13 | Production Readiness Board + RC tag | G9 | FDE4 chairs | FDE3 tech · FDE5 sec · FDE1 release | P9 | B | G9 release decision sign | Domain sign-off | G9 tech — RC tag + manifest | Author G9 — chair Production Readiness Board | G9 security sign
D14 | Buffer / defect burn-down (optional) | — | — | — | P9 | B | Defect burn-down / buffer | Defect burn-down / buffer | Defect burn-down / buffer | Defect burn-down / buffer | Defect burn-down / buffer

## Phase_Tasks
Task ID | Phase | Phase Name | Hours | Exit Gate | Track | Option B+ Days | Seat | Stream | Focus / Work Package | Status | % Complete | Owner Name | Reviewer | Blockers / Remarks | Actual Completion
PH-P0-FDE1 | P0 | Preflight | 0–2 | Preflight | A | D1 | FDE1 | Value (V) | Charter / plan ratification | Not Started | 0
PH-P0-FDE2 | P0 | Preflight | 0–2 | Preflight | A | D1 | FDE2 | Domain (D) | Case + inject skim | Not Started | 0
PH-P0-FDE3 | P0 | Preflight | 0–2 | Preflight | A | D1 | FDE3 | Architecture (A) | Scaffold + Hour-0 archive | Not Started | 0
PH-P0-FDE4 | P0 | Preflight | 0–2 | Preflight | A | D1 | FDE4 | GxP / Quality (Q) | Constraints catalogue | Not Started | 0
PH-P0-FDE5 | P0 | Preflight | 0–2 | Preflight | A | D1 | FDE5 | Security / Eval (S) | Constraints catalogue | Not Started | 0
PH-P1-FDE1 | P1 | Discovery | 2–7 | G1 | A | D1, D2 | FDE1 | Value (V) | Author G1 — artefacts 01–04 + production NFRs | Not Started | 0
PH-P1-FDE2 | P1 | Discovery | 2–7 | G1 | A | D1, D2 | FDE2 | Domain (D) | Inject skim support | Not Started | 0
PH-P1-FDE3 | P1 | Discovery | 2–7 | G1 | A | D1, D2 | FDE3 | Architecture (A) | Scripts skeleton | Not Started | 0
PH-P1-FDE4 | P1 | Discovery | 2–7 | G1 | A | D1, D2 | FDE4 | GxP / Quality (Q) | Must-review G1 — constraints catalogue | Not Started | 0
PH-P1-FDE5 | P1 | Discovery | 2–7 | G1 | A | D1, D2 | FDE5 | Security / Eval (S) | Must-review G1 — NFR / threat notes | Not Started | 0
PH-P2-FDE1 | P2 | Domain | 7–12 | G2 | A | D3, D4 | FDE1 | Value (V) | Must-review G2 | Not Started | 0
PH-P2-FDE2 | P2 | Domain | 7–12 | G2 | A | D3, D4 | FDE2 | Domain (D) | Author G2 — artefacts 05–08 + 84-inject register | Not Started | 0
PH-P2-FDE3 | P2 | Domain | 7–12 | G2 | A | D3, D4 | FDE3 | Architecture (A) | RTM / RELATIONSHIP_MODEL start | Not Started | 0
PH-P2-FDE4 | P2 | Domain | 7–12 | G2 | A | D3, D4 | FDE4 | GxP / Quality (Q) | Must-review G2 — authority / lineage | Not Started | 0
PH-P2-FDE5 | P2 | Domain | 7–12 | G2 | A | D3, D4 | FDE5 | Security / Eval (S) | Privacy / eval support (not G2 must-review) | Not Started | 0
PH-P3-FDE1 | P3 | Architecture | 12–18 | G3 | A | D5 | FDE1 | Value (V) | Architecture support (not G3 must-review) | Not Started | 0
PH-P3-FDE2 | P3 | Architecture | 12–18 | G3 | A | D5 | FDE2 | Domain (D) | Must-review G3 — RTM 09 + language | Not Started | 0
PH-P3-FDE3 | P3 | Architecture | 12–18 | G3 | A | D5 | FDE3 | Architecture (A) | Author G3 — artefacts 10–12 + evidence-resolver | Not Started | 0
PH-P3-FDE4 | P3 | Architecture | 12–18 | G3 | A | D5 | FDE4 | GxP / Quality (Q) | Co-author G3 — artefacts 13–15 GxP/CSA/QRM | Not Started | 0
PH-P3-FDE5 | P3 | Architecture | 12–18 | G3 | A | D5 | FDE5 | Security / Eval (S) | Must-review G3 — threat skeleton + contract tests | Not Started | 0
PH-P4-FDE1 | P4 | Secure design | 18–23 | G4 | A | D6, D7 | FDE1 | Value (V) | Must-review G4 — artefact 18 RAI | Not Started | 0
PH-P4-FDE2 | P4 | Secure design | 18–23 | G4 | A | D6, D7 | FDE2 | Domain (D) | Domain support (not G4 must-review) | Not Started | 0
PH-P4-FDE3 | P4 | Secure design | 18–23 | G4 | A | D6, D7 | FDE3 | Architecture (A) | Must-review G4 — Cursor evidence; build prep | Not Started | 0
PH-P4-FDE4 | P4 | Secure design | 18–23 | G4 | A | D6, D7 | FDE4 | GxP / Quality (Q) | Co-author G4 — artefacts 19–21 ISO / EU AI Act | Not Started | 0
PH-P4-FDE5 | P4 | Secure design | 18–23 | G4 | A | D6, D7 | FDE5 | Security / Eval (S) | Author G4 — artefacts 16–17 + failing prohibited tests | Not Started | 0
PH-P5-FDE1 | P5 | POC build | 23–31 | G5 | A | D8, D9 | FDE1 | Value (V) | Must-review G5 — Workflow C domain + UX | Not Started | 0
PH-P5-FDE2 | P5 | POC build | 23–31 | G5 | A | D8, D9 | FDE2 | Domain (D) | Workflow B domain rules | Not Started | 0
PH-P5-FDE3 | P5 | POC build | 23–31 | G5 | A | D8, D9 | FDE3 | Architecture (A) | Author G5 — build A→C→B + app + scripts | Not Started | 0
PH-P5-FDE4 | P5 | POC build | 23–31 | G5 | A | D8, D9 | FDE4 | GxP / Quality (Q) | Must-review G5 — Workflow A readiness rules | Not Started | 0
PH-P5-FDE5 | P5 | POC build | 23–31 | G5 | A | D8, D9 | FDE5 | Security / Eval (S) | Golden / edge / adversarial tests | Not Started | 0
PH-P6-FDE1 | P6 | TEVV | 31–35 | G6 | A | D10 | FDE1 | Value (V) | FinOps 23 + delivery FinOps | Not Started | 0
PH-P6-FDE2 | P6 | TEVV | 31–35 | G6 | A | D10 | FDE2 | Domain (D) | Must-review G6 — clinical / PV inject suites | Not Started | 0
PH-P6-FDE3 | P6 | TEVV | 31–35 | G6 | A | D10 | FDE3 | Architecture (A) | Must-review G6 — adapter wire + outage path | Not Started | 0
PH-P6-FDE4 | P6 | TEVV | 31–35 | G6 | A | D10 | FDE4 | GxP / Quality (Q) | Reg-authority suites | Not Started | 0
PH-P6-FDE5 | P6 | TEVV | 31–35 | G6 | A | D10 | FDE5 | Security / Eval (S) | Author G6 — runner / graders / policies / reports | Not Started | 0
PH-P7-FDE1 | P7 | Ops + clean-room | 35–38 | G7 | A | D10 | FDE1 | Value (V) | 26 TOM + 29 runway (G7 full-team review) | Not Started | 0
PH-P7-FDE2 | P7 | Ops + clean-room | 35–38 | G7 | A | D10 | FDE2 | Domain (D) | Domain freeze sign (G7 full-team review) | Not Started | 0
PH-P7-FDE3 | P7 | Ops + clean-room | 35–38 | G7 | A | D10 | FDE3 | Architecture (A) | Author G7 — evidence files + clean-room | Not Started | 0
PH-P7-FDE4 | P7 | Ops + clean-room | 35–38 | G7 | A | D10 | FDE4 | GxP / Quality (Q) | 27/28 draft (G7 full-team review) | Not Started | 0
PH-P7-FDE5 | P7 | Ops + clean-room | 35–38 | G7 | A | D10 | FDE5 | Security / Eval (S) | Co-author G7 — runbooks + eval evidence | Not Started | 0
PH-P8-FDE1 | P8 | Defence | 38–40 | G8 | A | D10 | FDE1 | Value (V) | Author G8 — pitch 30 + ship decision | Not Started | 0
PH-P8-FDE2 | P8 | Defence | 38–40 | G8 | A | D10 | FDE2 | Domain (D) | Defence domain demos (G8 full-team review) | Not Started | 0
PH-P8-FDE3 | P8 | Defence | 38–40 | G8 | A | D10 | FDE3 | Architecture (A) | Freeze + hash (G8 full-team review) | Not Started | 0
PH-P8-FDE4 | P8 | Defence | 38–40 | G8 | A | D10 | FDE4 | GxP / Quality (Q) | GxP defence proof (G8 full-team review) | Not Started | 0
PH-P8-FDE5 | P8 | Defence | 38–40 | G8 | A | D10 | FDE5 | Security / Eval (S) | Red-team / outage demos (G8 full-team review) | Not Started | 0
PH-P9-FDE1 | P9 | Production hardening | +16–24 | G9 | B | D11, D12, D13, D14 | FDE1 | Value (V) | G9 release decision / L1 runbook | Not Started | 0
PH-P9-FDE2 | P9 | Production hardening | +16–24 | G9 | B | D11, D12, D13, D14 | FDE2 | Domain (D) | RC domain regression | Not Started | 0
PH-P9-FDE3 | P9 | Production hardening | +16–24 | G9 | B | D11, D12, D13, D14 | FDE3 | Architecture (A) | G9 tech — RC packaging / rollback / tag | Not Started | 0
PH-P9-FDE4 | P9 | Production hardening | +16–24 | G9 | B | D11, D12, D13, D14 | FDE4 | GxP / Quality (Q) | Author G9 — chair Readiness Board 28 | Not Started | 0
PH-P9-FDE5 | P9 | Production hardening | +16–24 | G9 | B | D11, D12, D13, D14 | FDE5 | Security / Eval (S) | G9 security sign — SLO / sec retest | Not Started | 0

## Day_Tasks
Task ID | Day | Day Focus | Gate | Phase(s) | Track | Seat | Stream | Focus / Work Package | Status | % Complete | Owner Name | Reviewer | Dependencies | Blockers / Remarks | Actual Completion
DY-D1-FDE1 | D1 | Preflight + SCQA start | — | P0/P1 | A | FDE1 | Value (V) | SCQA start | Not Started | 0
DY-D1-FDE2 | D1 | Preflight + SCQA start | — | P0/P1 | A | FDE2 | Domain (D) | Case read | Not Started | 0
DY-D1-FDE3 | D1 | Preflight + SCQA start | — | P0/P1 | A | FDE3 | Architecture (A) | Scaffold + Hour-0 baseline archive | Not Started | 0
DY-D1-FDE4 | D1 | Preflight + SCQA start | — | P0/P1 | A | FDE4 | GxP / Quality (Q) | Constraints catalogue start | Not Started | 0
DY-D1-FDE5 | D1 | Preflight + SCQA start | — | P0/P1 | A | FDE5 | Security / Eval (S) | Constraints / NFR notes start | Not Started | 0
DY-D2-FDE1 | D2 | Business case, stakeholders, blueprint, prod NFRs | G1 | P1 | A | FDE1 | Value (V) | Author G1 — business case / NFRs / artefacts 01–04 | Not Started | 0
DY-D2-FDE2 | D2 | Business case, stakeholders, blueprint, prod NFRs | G1 | P1 | A | FDE2 | Domain (D) | Inject skim support | Not Started | 0
DY-D2-FDE3 | D2 | Business case, stakeholders, blueprint, prod NFRs | G1 | P1 | A | FDE3 | Architecture (A) | Scripts skeleton | Not Started | 0
DY-D2-FDE4 | D2 | Business case, stakeholders, blueprint, prod NFRs | G1 | P1 | A | FDE4 | GxP / Quality (Q) | Must-review G1 (with FDE5) | Not Started | 0
DY-D2-FDE5 | D2 | Business case, stakeholders, blueprint, prod NFRs | G1 | P1 | A | FDE5 | Security / Eval (S) | Must-review G1 — NFR lock (with FDE4) | Not Started | 0
DY-D3-FDE1 | D3 | DDD + data gov + brownfield | — | P2 | A | FDE1 | Value (V) | Stakeholder / value support | Not Started | 0
DY-D3-FDE2 | D3 | DDD + data gov + brownfield | — | P2 | A | FDE2 | Domain (D) | DDD + data gov (05–06) | Not Started | 0
DY-D3-FDE3 | D3 | DDD + data gov + brownfield | — | P2 | A | FDE3 | Architecture (A) | Brownfield map / RTM start | Not Started | 0
DY-D3-FDE4 | D3 | DDD + data gov + brownfield | — | P2 | A | FDE4 | GxP / Quality (Q) | Authority notes | Not Started | 0
DY-D3-FDE5 | D3 | DDD + data gov + brownfield | — | P2 | A | FDE5 | Security / Eval (S) | Eval dataset design start | Not Started | 0
DY-D4-FDE1 | D4 | Ontology + KG + inject map | G2 | P2 | A | FDE1 | Value (V) | Must-review G2 (with FDE4) | Not Started | 0
DY-D4-FDE2 | D4 | Ontology + KG + inject map | G2 | P2 | A | FDE2 | Domain (D) | Author G2 — ontology / KG / inject map | Not Started | 0
DY-D4-FDE3 | D4 | Ontology + KG + inject map | G2 | P2 | A | FDE3 | Architecture (A) | RELATIONSHIP_MODEL checker start | Not Started | 0
DY-D4-FDE4 | D4 | Ontology + KG + inject map | G2 | P2 | A | FDE4 | GxP / Quality (Q) | Must-review G2 — authority / lineage | Not Started | 0
DY-D4-FDE5 | D4 | Ontology + KG + inject map | G2 | P2 | A | FDE5 | Security / Eval (S) | Privacy / eval support (not G2 must-review) | Not Started | 0
DY-D5-FDE1 | D5 | C4 + ADR + contracts + GxP | G3 | P3 | A | FDE1 | Value (V) | Architecture support (not G3 must-review) | Not Started | 0
DY-D5-FDE2 | D5 | C4 + ADR + contracts + GxP | G3 | P3 | A | FDE2 | Domain (D) | Must-review G3 — RTM 09 + language | Not Started | 0
DY-D5-FDE3 | D5 | C4 + ADR + contracts + GxP | G3 | P3 | A | FDE3 | Architecture (A) | Author G3 — C4 / ADR / contracts / resolver | Not Started | 0
DY-D5-FDE4 | D5 | C4 + ADR + contracts + GxP | G3 | P3 | A | FDE4 | GxP / Quality (Q) | Co-author G3 — GxP artefacts 13–15 | Not Started | 0
DY-D5-FDE5 | D5 | C4 + ADR + contracts + GxP | G3 | P3 | A | FDE5 | Security / Eval (S) | Must-review G3 — threat skeleton + contract tests | Not Started | 0
DY-D6-FDE1 | D6 | Threat modelling + privacy + security tests | — | P4 | A | FDE1 | Value (V) | RAI 18 draft (prep for G4 must-review) | Not Started | 0
DY-D6-FDE2 | D6 | Threat modelling + privacy + security tests | — | P4 | A | FDE2 | Domain (D) | Domain support for threat model (not G4 must-review) | Not Started | 0
DY-D6-FDE3 | D6 | Threat modelling + privacy + security tests | — | P4 | A | FDE3 | Architecture (A) | Build prep / Cursor evidence (prep for G4 must-review) | Not Started | 0
DY-D6-FDE4 | D6 | Threat modelling + privacy + security tests | — | P4 | A | FDE4 | GxP / Quality (Q) | Privacy / QRM support (prep for G4 co-author) | Not Started | 0
DY-D6-FDE5 | D6 | Threat modelling + privacy + security tests | — | P4 | A | FDE5 | Security / Eval (S) | Threat modelling + privacy + security tests | Not Started | 0
DY-D7-FDE1 | D7 | ISO 42001 + EU AI Act + assurance + human factors | G4 | P4 | A | FDE1 | Value (V) | Must-review G4 (with FDE3) | Not Started | 0
DY-D7-FDE2 | D7 | ISO 42001 + EU AI Act + assurance + human factors | G4 | P4 | A | FDE2 | Domain (D) | Domain support (not G4 must-review) | Not Started | 0
DY-D7-FDE3 | D7 | ISO 42001 + EU AI Act + assurance + human factors | G4 | P4 | A | FDE3 | Architecture (A) | Must-review G4 (with FDE1) | Not Started | 0
DY-D7-FDE4 | D7 | ISO 42001 + EU AI Act + assurance + human factors | G4 | P4 | A | FDE4 | GxP / Quality (Q) | Co-author G4 — ISO / EU AI Act / assurance | Not Started | 0
DY-D7-FDE5 | D7 | ISO 42001 + EU AI Act + assurance + human factors | G4 | P4 | A | FDE5 | Security / Eval (S) | Author G4 — failing prohibited tests | Not Started | 0
DY-D8-FDE1 | D8 | Build WF A (+ resolver) + app shell; start C | — | P5 | A | FDE1 | Value (V) | Supply path start (WF C domain) | Not Started | 0
DY-D8-FDE2 | D8 | Build WF A (+ resolver) + app shell; start C | — | P5 | A | FDE2 | Domain (D) | WF B domain prep | Not Started | 0
DY-D8-FDE3 | D8 | Build WF A (+ resolver) + app shell; start C | — | P5 | A | FDE3 | Architecture (A) | WF A + evidence-resolver + app shell; start C | Not Started | 0
DY-D8-FDE4 | D8 | Build WF A (+ resolver) + app shell; start C | — | P5 | A | FDE4 | GxP / Quality (Q) | WF A readiness rules | Not Started | 0
DY-D8-FDE5 | D8 | Build WF A (+ resolver) + app shell; start C | — | P5 | A | FDE5 | Security / Eval (S) | Tests for WF A / prohibited paths | Not Started | 0
DY-D9-FDE1 | D9 | Finish C + B; AI-disabled; MVP demo | G5 | P5 | A | FDE1 | Value (V) | Must-review G5 — WF C + MVP demo | Not Started | 0
DY-D9-FDE2 | D9 | Finish C + B; AI-disabled; MVP demo | G5 | P5 | A | FDE2 | Domain (D) | WF B domain rules | Not Started | 0
DY-D9-FDE3 | D9 | Finish C + B; AI-disabled; MVP demo | G5 | P5 | A | FDE3 | Architecture (A) | Author G5 — finish C + B; AI-disabled scripts | Not Started | 0
DY-D9-FDE4 | D9 | Finish C + B; AI-disabled; MVP demo | G5 | P5 | A | FDE4 | GxP / Quality (Q) | Must-review G5 — WF A rules finalize | Not Started | 0
DY-D9-FDE5 | D9 | Finish C + B; AI-disabled; MVP demo | G5 | P5 | A | FDE5 | Security / Eval (S) | AI-disabled tests + MVP test evidence | Not Started | 0
DY-D10-FDE1 | D10 | TEVV / FinOps / clean-room / defence | G6–G8 | P6/P7/P8 | A | FDE1 | Value (V) | Author G8 — FinOps + defence pitch (also G7 full-team) | Not Started | 0
DY-D10-FDE2 | D10 | TEVV / FinOps / clean-room / defence | G6–G8 | P6/P7/P8 | A | FDE2 | Domain (D) | Must-review G6 — inject suites (clinical/PV); G7/G8 full-team | Not Started | 0
DY-D10-FDE3 | D10 | TEVV / FinOps / clean-room / defence | G6–G8 | P6/P7/P8 | A | FDE3 | Architecture (A) | Must-review G6; Author G7 — clean-room / freeze; G8 full-team | Not Started | 0
DY-D10-FDE4 | D10 | TEVV / FinOps / clean-room / defence | G6–G8 | P6/P7/P8 | A | FDE4 | GxP / Quality (Q) | Assurance + GxP defence proof (G7/G8 full-team) | Not Started | 0
DY-D10-FDE5 | D10 | TEVV / FinOps / clean-room / defence | G6–G8 | P6/P7/P8 | A | FDE5 | Security / Eval (S) | Author G6 — TEVV reports; Co-author G7; G8 full-team | Not Started | 0
DY-D11-FDE1 | D11 | P9: SLO, runbooks, packaging | — | P9 | B | FDE1 | Value (V) | Support runbooks (L1) | Not Started | 0
DY-D11-FDE2 | D11 | P9: SLO, runbooks, packaging | — | P9 | B | FDE2 | Domain (D) | RC domain regression prep | Not Started | 0
DY-D11-FDE3 | D11 | P9: SLO, runbooks, packaging | — | P9 | B | FDE3 | Architecture (A) | App packaging & config | Not Started | 0
DY-D11-FDE4 | D11 | P9: SLO, runbooks, packaging | — | P9 | B | FDE4 | GxP / Quality (Q) | Accessibility smoke prep | Not Started | 0
DY-D11-FDE5 | D11 | P9: SLO, runbooks, packaging | — | P9 | B | FDE5 | Security / Eval (S) | Observability & SLOs | Not Started | 0
DY-D12-FDE1 | D12 | P9: security retest, backup/restore, rollback | — | P9 | B | FDE1 | Value (V) | Release decision draft | Not Started | 0
DY-D12-FDE2 | D12 | P9: security retest, backup/restore, rollback | — | P9 | B | FDE2 | Domain (D) | Domain regression execute | Not Started | 0
DY-D12-FDE3 | D12 | P9: security retest, backup/restore, rollback | — | P9 | B | FDE3 | Architecture (A) | Backup/restore + rollback evidence | Not Started | 0
DY-D12-FDE4 | D12 | P9: security retest, backup/restore, rollback | — | P9 | B | FDE4 | GxP / Quality (Q) | Residual risk draft | Not Started | 0
DY-D12-FDE5 | D12 | P9: security retest, backup/restore, rollback | — | P9 | B | FDE5 | Security / Eval (S) | Security retest + backup/restore | Not Started | 0
DY-D13-FDE1 | D13 | Production Readiness Board + RC tag | G9 | P9 | B | FDE1 | Value (V) | G9 release decision sign | Not Started | 0
DY-D13-FDE2 | D13 | Production Readiness Board + RC tag | G9 | P9 | B | FDE2 | Domain (D) | Domain sign-off | Not Started | 0
DY-D13-FDE3 | D13 | Production Readiness Board + RC tag | G9 | P9 | B | FDE3 | Architecture (A) | G9 tech — RC tag + manifest | Not Started | 0
DY-D13-FDE4 | D13 | Production Readiness Board + RC tag | G9 | P9 | B | FDE4 | GxP / Quality (Q) | Author G9 — chair Production Readiness Board | Not Started | 0
DY-D13-FDE5 | D13 | Production Readiness Board + RC tag | G9 | P9 | B | FDE5 | Security / Eval (S) | G9 security sign | Not Started | 0
DY-D14-FDE1 | D14 | Buffer / defect burn-down (optional) | — | P9 | B | FDE1 | Value (V) | Defect burn-down / buffer | Not Started | 0
DY-D14-FDE2 | D14 | Buffer / defect burn-down (optional) | — | P9 | B | FDE2 | Domain (D) | Defect burn-down / buffer | Not Started | 0
DY-D14-FDE3 | D14 | Buffer / defect burn-down (optional) | — | P9 | B | FDE3 | Architecture (A) | Defect burn-down / buffer | Not Started | 0
DY-D14-FDE4 | D14 | Buffer / defect burn-down (optional) | — | P9 | B | FDE4 | GxP / Quality (Q) | Defect burn-down / buffer | Not Started | 0
DY-D14-FDE5 | D14 | Buffer / defect burn-down (optional) | — | P9 | B | FDE5 | Security / Eval (S) | Defect burn-down / buffer | Not Started | 0

## Gate_RACI
Gate | Checkpoint Question / Exit | Author / Chair | Must Review | Phase | Day | Status | Decision (PASS/FAIL/CONDITIONAL) | Remediation Notes | Signed By | Date
Preflight | Package + charter; Hour-0 baseline | All | — | P0 | D1 | Not Started
G1 | Problem measurable; no-AI honest; NFRs locked? | FDE1 | FDE4 + FDE5 | P1 | D2 | Not Started
G2 | Conflicts tracked not silently resolved; inject register real? | FDE2 | FDE1 + FDE4 | P2 | D4 | Not Started
G3 | Prohibited actions outside executable boundary? | FDE3 + FDE4 | FDE2 + FDE5 | P3 | D5 | Not Started
G4 | Threat/privacy/ISO controls + failing prohibited tests? Agents unlock after PASS | FDE5 + FDE4 | FDE1 + FDE3 | P4 | D7 | Not Started
G5 | Three workflows run offline against fixtures? | FDE3 + domain | FDE1 + FDE4 | P5 | D9 | Not Started
G6 | Red-team / outage / cost gates fail closed? | FDE5 | FDE2 + FDE3 | P6 | D10 | Not Started
G7 | Clean-room + --final + hash --check? | FDE3 + FDE5 | Full team + outsider | P7 | D10 | Not Started
G8 | 13 defence elements rehearsed; recommendation clear? | FDE1 leads | Full team | P8 | D10 | Not Started
G9 | Readiness Board; Blockers=0; RC clean-room? | FDE4 chairs | FDE3 tech · FDE5 sec · FDE1 release | P9 | D13 | Not Started

## Workflow_RACI
Workflow | Name | Domain Owner | Builder | Security | Sign-off | Contract | Build Order | Status | Notes
A | Batch evidence | FDE4 | FDE3 | FDE5 | FDE4 | batch_response.schema.json | 1 | Not Started | execution_status must remain not_executed; no prohibited autonomy
B | PV intake | FDE2 | FDE3 | FDE5 | FDE2 + FDE4 | pv_response.schema.json | 3 | Not Started | execution_status must remain not_executed; no prohibited autonomy
C | Supply options | FDE1 | FDE3 | FDE5 | FDE1 + FDE4 | supply_response.schema.json | 2 | Not Started | execution_status must remain not_executed; no prohibited autonomy
Shared | authZ / contracts / evidence-resolver | — | FDE3 | FDE5 | FDE5 + FDE4 | shared modules | 0 | Not Started | execution_status must remain not_executed; no prohibited autonomy
Forbidden on all workflows: release/reject/reprocess/relabel/recall; final PV seriousness/causality/expectedness/reportability/signal confirm; reserve/allocate/ship/quality-status change. Build order: Shared → A → C → B.

## Owes
Seat | Stream | By G8 (Defence) | Extra by G9 (Track B) | G8 Status | G9 Status | Owner Name | Notes
FDE1 | Value (V) | 01–04, 26, 29, 30; WF C | Release decision; L1 runbook; G9 minutes | Not Started | Not Started
FDE2 | Domain (D) | 05–08; inject map; WF B | RC domain regression sign-off | Not Started | Not Started
FDE3 | Architecture (A) | 09–12; app/src/scripts; clean-room | RC tag, packaging, rollback, manifest | Not Started | Not Started
FDE4 | GxP / Quality (Q) | 13–15, 19–21; WF A; GxP proof | Chair 28 board; residual risk sign | Not Started | Not Started
FDE5 | Security / Eval (S) | 16–18, 22–25, 27; security tests | SLO/observability; RC retest; G9 sec sign | Not Started | Not Started